## Pivot Table
Row Labels | Sum of Planned Budget | Sum of Actual Cost | Sum of Cost Variance
Cancelled | 7000 | 400 | 6600
Completed | 750000 | 820000 | -70000
Delayed | 36000 | 20100 | 15900
In Progress | 232000 | 102100 | 129900
Not Started | 474000 | 0 | 474000
On Hold | 24000 | 11600 | 12400
Grand Total | 1523000 | 954200 | 568800
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Management
Project Name | Task Name | Assigned To | Priority | Planned Start Date | Planned End Date | Actual End Date | % Complete | Planned Budget | Actual Cost | Status | Cost Variance | Budget Status | Timeline
Compliance Overhaul | Deployment Planning | Chris Evans | Medium | 2024-04-05 | 2024-04-27 | 2024-05-24 | 100% | 40000 | 40800 | Completed | -800 | Over Budget | 27
Marketing Automation | Bug Fixes | Brian Taylor | Medium | 2024-01-04 | 2024-01-24 |  | 23% | 34000 | 17900 | Delayed | 16100 | Within Budget | 971
Security Audit | Competitive Analysis | Elena Rodriguez | Low | 2024-10-14 | 2024-10-21 | 2024-10-24 | 100% | 2000 | 1800 | Completed | 200 | Within Budget | 3
Email Platform Migration | Budget Review | Rachel Thompson | Medium | 2024-04-24 | 2024-05-09 | 2024-04-28 | 30% | 18000 | 2700 | Cancelled | 15300 | Within Budget | -11
Security Audit | Competitive Analysis | Natasha Singh | Medium | 2025-01-10 | 2025-02-12 | 2025-02-11 | 100% | 31000 | 32500 | Completed | -1500 | Over Budget | -1
Inventory System | Risk Assessment | Hannah White | Critical | 2025-01-25 | 2025-02-28 | 2025-02-25 | 100% | 100000 | 116000 | Completed | -16000 | Over Budget | -3
Onboarding Automation | System Configuration | Emily Davis | High | 2024-11-19 | 2024-12-05 | 2024-11-23 | 10% | 44000 | 12900 | Cancelled | 31100 | Within Budget | -12
Budget Planning Tool | A/B Testing Setup | Jennifer Lee | Medium | 2024-06-10 | 2024-06-19 | 2024-06-14 | 10% | 14000 | 1200 | Cancelled | 12800 | Within Budget | -5
Inventory System | SEO Optimization | James Wilson | Low | 2024-04-07 | 2024-05-04 | 2024-04-13 | 10% | 16000 | 4500 | Cancelled | 11500 | Within Budget | -21
Analytics Dashboard | Frontend Development | Kevin O'Brien | Low | 2024-06-26 | 2024-09-12 | 2024-09-23 | 100% | 149000 | 198400 | Completed | -49400 | Over Budget | 11
Onboarding Automation | Frontend Development | Kevin O'Brien | Medium | 2024-04-10 | 2024-05-12 | 2024-04-15 | 25% | 49000 | 8200 | Cancelled | 40800 | Within Budget | -27
Website Redesign | API Development | Jessica Turner | Medium | 2025-06-19 | 2025-06-30 |  | 0% | 32000 | 0 | Not Started | 32000 | Within Budget | 448
Security Audit | User Training | Jennifer Lee | Medium | 2025-01-07 | 2025-01-25 | 2025-02-07 | 100% | 34000 | 33300 | Completed | 700 | Within Budget | 13
Customer Portal | User Acceptance Testing | Lisa Wang | Medium | 2024-04-30 | 2024-05-11 | 2024-05-01 | 10% | 22000 | 1400 | Cancelled | 20600 | Within Budget | -10
Office Relocation | Frontend Development | Amanda Foster | Medium | 2025-01-21 | 2025-04-16 |  | 48% | 81000 | 96700 | Delayed | -15700 | Over Budget | 523
Chatbot Development | Content Creation | Hannah White | Medium | 2024-03-21 | 2024-04-14 | 2024-03-26 | 10% | 32000 | 12600 | Cancelled | 19400 | Within Budget | -19
Inventory System | Content Creation | Chris Evans | Medium | 2024-01-30 | 2024-02-08 | 2024-03-24 | 100% | 10000 | 13100 | Completed | -3100 | Over Budget | 45
Supply Chain Optimization | Budget Review | Lisa Wang | Medium | 2025-04-21 | 2025-05-17 |  | 0% | 48000 | 0 | Not Started | 48000 | Within Budget | 492
Compliance Overhaul | Performance Testing | Chris Evans | High | 2024-07-17 | 2024-07-24 | 2024-07-28 | 100% | 11000 | 10200 | Completed | 800 | Within Budget | 4
Security Audit | Wireframing | Marcus Johnson | High | 2024-08-27 | 2024-09-28 | 2024-09-09 | 25% | 43000 | 12200 | Cancelled | 30800 | Within Budget | -19
Chatbot Development | Deployment Planning | Robert Garcia | Medium | 2024-08-18 | 2024-09-03 | 2024-09-13 | 100% | 36000 | 39300 | Completed | -3300 | Over Budget | 10
Cloud Infrastructure | Requirements Gathering | James Wilson | Low | 2024-02-08 | 2024-02-22 | 2024-02-23 | 100% | 19000 | 23500 | Completed | -4500 | Over Budget | 1
Email Platform Migration | Technical Architecture | Jessica Turner | Low | 2024-12-24 | 2025-01-23 |  | 79% | 31000 | 21300 | In Progress | 9700 | Within Budget | 606
CRM Migration | Technical Architecture | Marcus Johnson | High | 2024-12-30 | 2025-01-25 |  | 93% | 10000 | 8900 | In Progress | 1100 | Within Budget | 604
Analytics Dashboard | User Acceptance Testing | Stephanie Adams | Medium | 2024-04-21 | 2024-05-25 |  | 37% | 66000 | 78400 | Delayed | -12400 | Over Budget | 849
Performance Review System | Quality Assurance | Emily Davis | Low | 2024-06-18 | 2024-07-09 | 2024-06-25 | 20% | 32000 | 7700 | Cancelled | 24300 | Within Budget | -14
Budget Planning Tool | Retrospective | Daniel Park | High | 2024-12-08 | 2024-12-20 |  | 45% | 45000 | 33900 | Delayed | 11100 | Within Budget | 640
Social Media Revamp | Data Migration | Lisa Wang | Medium | 2025-03-29 | 2025-06-04 |  | 69% | 81000 | 51100 | In Progress | 29900 | Within Budget | 474
Performance Review System | Post-Launch Review | Rachel Thompson | Medium | 2025-02-22 | 2025-03-22 |  | 32% | 44000 | 53800 | Delayed | -9800 | Over Budget | 548
Email Platform Migration | Go-Live Preparation | Marcus Johnson | Medium | 2025-04-29 | 2025-05-25 |  | 0% | 28000 | 0 | Not Started | 28000 | Within Budget | 484
Compliance Overhaul | Code Review | Amanda Foster | Critical | 2024-04-01 | 2024-04-10 | 2024-04-03 | 100% | 2000 | 2000 | Completed | 0 | Within Budget | -7
Annual Report | Integration Testing | Chris Evans | Medium | 2025-05-07 | 2025-06-08 |  | 0% | 37000 | 0 | Not Started | 37000 | Within Budget | 470
Compliance Overhaul | API Development | Amanda Foster | High | 2024-05-21 | 2024-06-17 | 2024-06-24 | 100% | 47000 | 43000 | Completed | 4000 | Within Budget | 7
Mobile App Launch | Stakeholder Interviews | Lisa Wang | High | 2024-05-05 | 2024-05-20 | 2024-06-04 | 100% | 42000 | 44400 | Completed | -2400 | Over Budget | 15
ERP Implementation | Compliance Check | Amanda Foster | High | 2024-02-15 | 2024-03-15 | 2024-03-15 | 100% | 15000 | 17300 | Completed | -2300 | Over Budget | 0
Product Launch Q2 | Frontend Development | Daniel Park | High | 2024-03-15 | 2024-05-24 | 2024-06-12 | 100% | 67000 | 92200 | Completed | -25200 | Over Budget | 19
Office Relocation | User Acceptance Testing | Marcus Johnson | High | 2025-01-21 | 2025-02-19 | 2025-02-27 | 100% | 17000 | 22400 | Completed | -5400 | Over Budget | 8
CRM Migration | Wireframing | Jessica Turner | High | 2024-09-13 | 2024-10-13 | 2024-11-27 | 100% | 24000 | 23100 | Completed | 900 | Within Budget | 45
Chatbot Development | Backup Configuration | Robert Garcia | Medium | 2024-05-17 | 2024-06-07 | 2024-06-19 | 100% | 11000 | 13400 | Completed | -2400 | Over Budget | 12
Mobile App Launch | Analytics Integration | Daniel Park | Medium | 2025-03-15 | 2025-03-23 |  | 0% | 9000 | 0 | Not Started | 9000 | Within Budget | 547
Inventory System | Bug Fixes | Robert Garcia | Medium | 2024-11-09 | 2024-11-16 | 2024-11-12 | 0% | 4000 | 700 | Cancelled | 3300 | Within Budget | -4
Annual Report | Feedback Collection | Rachel Thompson | Medium | 2025-05-04 | 2025-05-24 |  | 0% | 33000 | 0 | Not Started | 33000 | Within Budget | 485
Inventory System | Deployment Planning | Robert Garcia | Low | 2024-03-07 | 2024-04-03 | 2024-04-24 | 100% | 12000 | 13600 | Completed | -1600 | Over Budget | 21
Inventory System | Quality Assurance | Carlos Mendez | Medium | 2025-04-06 | 2025-05-02 |  | 94% | 49000 | 51800 | In Progress | -2800 | Over Budget | 507
Performance Review System | Accessibility Audit | James Wilson | Critical | 2025-06-22 | 2025-06-30 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 448
Product Launch Q2 | Backup Configuration | Lisa Wang | Low | 2024-09-03 | 2024-10-06 | 2024-09-28 | 100% | 39000 | 38300 | Completed | 700 | Within Budget | -8
Compliance Overhaul | Training Materials | Kevin O'Brien | Low | 2024-08-10 | 2024-09-08 | 2024-08-20 | 0% | 45000 | 6300 | Cancelled | 38700 | Within Budget | -19
Office Relocation | A/B Testing Setup | Robert Garcia | Medium | 2025-04-01 | 2025-04-26 |  | 0% | 29000 | 0 | Not Started | 29000 | Within Budget | 513
Chatbot Development | Retrospective | Elena Rodriguez | Medium | 2024-02-11 | 2024-02-23 | 2024-02-15 | 15% | 44000 | 8200 | Cancelled | 35800 | Within Budget | -8
Office Relocation | Database Design | Jessica Turner | High | 2025-01-03 | 2025-02-08 |  | 57% | 74000 | 48900 | In Progress | 25100 | Within Budget | 590
Training Platform | Requirements Gathering | Marcus Johnson | Critical | 2025-05-08 | 2025-05-13 |  | 0% | 9000 | 0 | Not Started | 9000 | Within Budget | 496
Mobile App Launch | Monitoring Setup | Kevin O'Brien | Critical | 2024-08-08 | 2024-09-07 | 2024-09-22 | 100% | 34000 | 44800 | Completed | -10800 | Over Budget | 15
Office Relocation | Data Migration | Emily Davis | Medium | 2024-11-16 | 2024-12-27 | 2025-02-09 | 100% | 60000 | 70700 | Completed | -10700 | Over Budget | 44
Analytics Dashboard | Status Reporting | Jessica Turner | Low | 2025-01-11 | 2025-01-27 |  | 41% | 47000 | 10200 | On Hold | 36800 | Within Budget | 602
Cloud Infrastructure | Security Review | Jessica Turner | Medium | 2025-06-12 | 2025-06-19 |  | 0% | 10000 | 0 | Not Started | 10000 | Within Budget | 459
Budget Planning Tool | Unit Testing | Jessica Turner | High | 2025-05-27 | 2025-06-11 |  | 0% | 25000 | 0 | Not Started | 25000 | Within Budget | 467
ERP Implementation | User Acceptance Testing | Tom Mitchell | Medium | 2024-06-20 | 2024-07-11 | 2024-07-25 | 100% | 32000 | 42800 | Completed | -10800 | Over Budget | 14
Office Relocation | Content Creation | Robert Garcia | Medium | 2024-09-04 | 2024-09-28 | 2024-10-06 | 100% | 25000 | 25700 | Completed | -700 | Over Budget | 8
Website Redesign | Wireframing | Natasha Singh | High | 2024-01-25 | 2024-02-22 | 2024-02-04 | 0% | 18000 | 2700 | Cancelled | 15300 | Within Budget | -18
Compliance Overhaul | Documentation | Lisa Wang | Medium | 2024-09-11 | 2024-10-11 | 2024-11-22 | 100% | 29000 | 27400 | Completed | 1600 | Within Budget | 42
Product Launch Q1 | Risk Assessment | Olivia Martinez | Low | 2024-08-08 | 2024-08-25 | 2024-09-15 | 100% | 13000 | 14900 | Completed | -1900 | Over Budget | 21
Chatbot Development | Budget Review | Jessica Turner | Medium | 2025-01-01 | 2025-01-23 |  | 63% | 13000 | 2800 | On Hold | 10200 | Within Budget | 606
Onboarding Automation | User Training | Brian Taylor | Medium | 2024-08-27 | 2024-09-12 | 2024-09-12 | 100% | 34000 | 38100 | Completed | -4100 | Over Budget | 0
Chatbot Development | Infrastructure Setup | Emily Davis | Medium | 2025-06-24 | 2025-07-07 |  | 0% | 11000 | 0 | Not Started | 11000 | Within Budget | 441
Cloud Infrastructure | Market Research | James Wilson | High | 2025-02-19 | 2025-03-01 |  | 42% | 15000 | 6900 | In Progress | 8100 | Within Budget | 569
Brand Refresh | Documentation | Olivia Martinez | High | 2024-11-13 | 2024-11-27 | 2024-11-25 | 100% | 40000 | 46700 | Completed | -6700 | Over Budget | -2
Mobile App Launch | Risk Assessment | Chris Evans | High | 2025-04-01 | 2025-04-14 |  | 48% | 27000 | 10500 | In Progress | 16500 | Within Budget | 525
Payment Integration | Market Research | Michael Brown | Medium | 2024-08-05 | 2024-08-10 |  | 70% | 5000 | 3000 | Delayed | 2000 | Within Budget | 772
Marketing Automation | Quality Assurance | Daniel Park | Low | 2025-04-06 | 2025-05-08 |  | 0% | 80000 | 0 | Not Started | 80000 | Within Budget | 501
Chatbot Development | SEO Optimization | David Kim | Critical | 2025-04-01 | 2025-05-04 |  | 29% | 39000 | 9100 | In Progress | 29900 | Within Budget | 505
Performance Review System | Status Reporting | Kevin O'Brien | Critical | 2024-12-10 | 2025-01-05 | 2024-12-22 | 0% | 19000 | 4400 | Cancelled | 14600 | Within Budget | -14
Payment Integration | Competitive Analysis | Rachel Thompson | Low | 2025-06-21 | 2025-07-14 |  | 0% | 11000 | 0 | Not Started | 11000 | Within Budget | 434
HR System Upgrade | Stakeholder Interviews | Tom Mitchell | High | 2025-05-31 | 2025-06-15 |  | 22% | 24000 | 4800 | In Progress | 19200 | Within Budget | 463
CRM Migration | Change Management | Carlos Mendez | Medium | 2024-12-23 | 2025-01-16 | 2025-02-16 | 100% | 19000 | 20600 | Completed | -1600 | Over Budget | 31
Data Warehouse Build | Feedback Collection | Elena Rodriguez | High | 2024-11-25 | 2024-12-19 | 2024-12-30 | 100% | 13000 | 15500 | Completed | -2500 | Over Budget | 11
Product Launch Q1 | Communication Plan | Chris Evans | Low | 2024-09-20 | 2024-10-19 | 2024-11-13 | 100% | 47000 | 51100 | Completed | -4100 | Over Budget | 25
Onboarding Automation | Analytics Integration | Priya Patel | Medium | 2025-04-14 | 2025-04-28 |  | 0% | 42000 | 0 | Not Started | 42000 | Within Budget | 511
Analytics Dashboard | Infrastructure Setup | Lisa Wang | Low | 2024-02-04 | 2024-03-09 | 2024-02-10 | 15% | 49000 | 8800 | Cancelled | 40200 | Within Budget | -28
Security Audit | Frontend Development | Sarah Chen | Medium | 2024-03-26 | 2024-05-10 | 2024-05-11 | 100% | 53000 | 63800 | Completed | -10800 | Over Budget | 1
Office Relocation | Security Review | Daniel Park | Low | 2025-02-05 | 2025-03-03 |  | 41% | 34000 | 16600 | In Progress | 17400 | Within Budget | 567
Security Audit | Data Migration | Jennifer Lee | High | 2025-01-03 | 2025-02-23 | 2025-04-09 | 100% | 94000 | 110700 | Completed | -16700 | Over Budget | 45
Chatbot Development | User Training | Chris Evans | High | 2024-02-03 | 2024-02-27 | 2024-02-27 | 100% | 25000 | 34600 | Completed | -9600 | Over Budget | 0
Inventory System | Code Review | Chris Evans | Low | 2024-05-24 | 2024-06-23 | 2024-08-01 | 100% | 30000 | 29700 | Completed | 300 | Within Budget | 39
Compliance Overhaul | Change Management | Rachel Thompson | Low | 2025-03-07 | 2025-04-01 |  | 41% | 47000 | 14300 | On Hold | 32700 | Within Budget | 538
Performance Review System | Accessibility Audit | Priya Patel | Low | 2025-01-24 | 2025-02-24 | 2025-03-31 | 100% | 59000 | 62100 | Completed | -3100 | Over Budget | 35
Email Platform Migration | Market Research | Ahmed Hassan | Low | 2025-06-04 | 2025-06-15 |  | 0% | 18000 | 0 | Not Started | 18000 | Within Budget | 463
CRM Migration | Asset Design | Ahmed Hassan | High | 2025-06-24 | 2025-07-20 |  | 0% | 22000 | 0 | Not Started | 22000 | Within Budget | 428
ERP Implementation | API Development | Hannah White | Low | 2024-12-14 | 2025-01-01 | 2024-12-20 | 10% | 28000 | 7200 | Cancelled | 20800 | Within Budget | -12
Analytics Dashboard | Post-Launch Review | Robert Garcia | Medium | 2024-12-24 | 2025-01-06 | 2024-12-28 | 25% | 15000 | 2500 | Cancelled | 12500 | Within Budget | -9
Marketing Automation | Asset Design | Priya Patel | Medium | 2025-02-13 | 2025-02-28 | 2025-02-28 | 100% | 35000 | 40500 | Completed | -5500 | Over Budget | 0
Chatbot Development | SEO Optimization | Jessica Turner | High | 2024-01-03 | 2024-02-02 | 2024-01-05 | 20% | 21000 | 2800 | Cancelled | 18200 | Within Budget | -28
HR System Upgrade | Go-Live Preparation | James Wilson | High | 2024-12-04 | 2025-01-01 | 2024-12-11 | 30% | 45000 | 16600 | Cancelled | 28400 | Within Budget | -21
Annual Report | Content Creation | Michael Brown | High | 2024-02-03 | 2024-02-24 | 2024-04-03 | 100% | 19000 | 24500 | Completed | -5500 | Over Budget | 39
CRM Migration | Security Review | Amanda Foster | Medium | 2025-06-25 | 2025-07-24 |  | 0% | 43000 | 0 | Not Started | 43000 | Within Budget | 424
Budget Planning Tool | Accessibility Audit | Chris Evans | Medium | 2025-05-05 | 2025-05-22 |  | 0% | 11000 | 0 | Not Started | 11000 | Within Budget | 487
Payment Integration | Frontend Development | Olivia Martinez | High | 2025-01-02 | 2025-02-14 |  | 39% | 31000 | 19100 | Delayed | 11900 | Within Budget | 584
Marketing Automation | Iteration Planning | Jessica Turner | High | 2024-06-28 | 2024-07-31 | 2024-07-04 | 10% | 42000 | 10600 | Cancelled | 31400 | Within Budget | -27
Social Media Revamp | Code Review | Stephanie Adams | Low | 2025-01-12 | 2025-02-08 | 2025-02-08 | 100% | 33000 | 43000 | Completed | -10000 | Over Budget | 0
Analytics Dashboard | Analytics Integration | Tom Mitchell | Medium | 2024-04-10 | 2024-04-22 | 2024-04-20 | 100% | 35000 | 37200 | Completed | -2200 | Over Budget | -2
Data Warehouse Build | Change Management | Chris Evans | High | 2024-02-12 | 2024-02-19 | 2024-02-24 | 100% | 6000 | 6800 | Completed | -800 | Over Budget | 5
ERP Implementation | Integration Testing | Brian Taylor | Medium | 2024-09-18 | 2024-10-23 | 2024-10-13 | 100% | 40000 | 46100 | Completed | -6100 | Over Budget | -10
Budget Planning Tool | Performance Testing | David Kim | High | 2024-09-18 | 2024-10-06 | 2024-10-13 | 100% | 15000 | 12900 | Completed | 2100 | Within Budget | 7
Security Audit | API Development | Jennifer Lee | Low | 2025-04-20 | 2025-05-15 |  | 0% | 35000 | 0 | Not Started | 35000 | Within Budget | 494
ERP Implementation | Analytics Integration | Elena Rodriguez | Medium | 2025-03-23 | 2025-04-13 |  | 0% | 24000 | 0 | Not Started | 24000 | Within Budget | 526
Product Launch Q1 | Contract Negotiation | Rachel Thompson | Medium | 2024-05-03 | 2024-05-20 | 2024-05-23 | 100% | 23000 | 22600 | Completed | 400 | Within Budget | 3
Training Platform | Market Research | Jennifer Lee | Low | 2024-12-25 | 2025-01-04 | 2025-01-04 | 100% | 9000 | 9700 | Completed | -700 | Over Budget | 0
Training Platform | Contract Negotiation | Amanda Foster | Low | 2024-12-03 | 2024-12-21 | 2025-01-30 | 100% | 36000 | 34300 | Completed | 1700 | Within Budget | 40
Marketing Automation | Wireframing | Hannah White | Medium | 2024-09-19 | 2024-10-20 | 2024-11-20 | 100% | 92000 | 115300 | Completed | -23300 | Over Budget | 31
Website Redesign | Optimization | Hannah White | High | 2024-02-28 | 2024-03-07 | 2024-02-28 | 100% | 15000 | 15500 | Completed | -500 | Over Budget | -8
Compliance Overhaul | Performance Testing | Amanda Foster | Low | 2025-01-31 | 2025-03-03 | 2025-03-16 | 100% | 69000 | 81500 | Completed | -12500 | Over Budget | 13
Onboarding Automation | Change Management | Olivia Martinez | High | 2024-03-27 | 2024-04-04 | 2024-04-05 | 100% | 8000 | 8800 | Completed | -800 | Over Budget | 1
CRM Migration | Infrastructure Setup | Jessica Turner | Medium | 2024-09-13 | 2024-09-30 | 2024-09-29 | 100% | 11000 | 10500 | Completed | 500 | Within Budget | -1
Annual Report | Code Review | Michael Brown | High | 2024-08-08 | 2024-09-05 | 2024-08-27 | 100% | 14000 | 19300 | Completed | -5300 | Over Budget | -9
Office Relocation | Retrospective | Robert Garcia | Medium | 2024-08-12 | 2024-08-18 | 2024-08-13 | 25% | 14000 | 5300 | Cancelled | 8700 | Within Budget | -5
Compliance Overhaul | System Configuration | Rachel Thompson | Medium | 2024-04-26 | 2024-05-08 | 2024-06-02 | 100% | 24000 | 25700 | Completed | -1700 | Over Budget | 25
Payment Integration | Training Materials | Amanda Foster | Low | 2025-02-18 | 2025-03-10 | 2025-03-01 | 100% | 41000 | 51700 | Completed | -10700 | Over Budget | -9
Vendor Portal | Go-Live Preparation | Natasha Singh | Medium | 2025-04-22 | 2025-05-04 |  | 47% | 30000 | 16700 | In Progress | 13300 | Within Budget | 505
Training Platform | Contract Negotiation | Elena Rodriguez | Medium | 2024-03-27 | 2024-04-28 |  | 57% | 97000 | 69600 | Delayed | 27400 | Within Budget | 876
Marketing Automation | Infrastructure Setup | Emily Davis | Critical | 2024-03-27 | 2024-04-18 | 2024-04-23 | 100% | 28000 | 27700 | Completed | 300 | Within Budget | 5
Security Audit | User Acceptance Testing | Priya Patel | Low | 2024-03-15 | 2024-04-04 | 2024-04-16 | 100% | 48000 | 51500 | Completed | -3500 | Over Budget | 12
Vendor Portal | Vendor Evaluation | Robert Garcia | Critical | 2024-06-10 | 2024-06-20 |  | 71% | 12000 | 10900 | Delayed | 1100 | Within Budget | 823
API Gateway | Security Review | Emily Davis | Medium | 2024-04-10 | 2024-05-14 |  | 23% | 54000 | 64800 | Delayed | -10800 | Over Budget | 860
Email Platform Migration | API Development | Sarah Chen | Low | 2025-06-01 | 2025-06-30 |  | 0% | 22000 | 0 | Not Started | 22000 | Within Budget | 448
Customer Portal | Frontend Development | Rachel Thompson | Low | 2024-02-22 | 2024-04-14 | 2024-04-15 | 100% | 52000 | 65000 | Completed | -13000 | Over Budget | 1
ERP Implementation | A/B Testing Setup | Carlos Mendez | Medium | 2024-03-13 | 2024-04-14 | 2024-04-05 | 100% | 36000 | 50300 | Completed | -14300 | Over Budget | -9
Product Launch Q2 | Training Materials | Olivia Martinez | High | 2024-06-19 | 2024-06-29 |  | 41% | 6000 | 6300 | Delayed | -300 | Over Budget | 814
Brand Refresh | Documentation | James Wilson | Medium | 2024-11-22 | 2024-12-19 | 2024-11-27 | 0% | 29000 | 8500 | Cancelled | 20500 | Within Budget | -22
CRM Migration | Asset Design | Kevin O'Brien | Low | 2024-11-19 | 2024-12-11 |  | 32% | 10000 | 10800 | Delayed | -800 | Over Budget | 649
Data Warehouse Build | Retrospective | Chris Evans | Medium | 2024-01-03 | 2024-01-17 |  | 33% | 13000 | 16300 | Delayed | -3300 | Over Budget | 978
DevOps Pipeline | Prototype Development | Natasha Singh | Medium | 2024-07-02 | 2024-07-21 |  | 79% | 11000 | 13300 | Delayed | -2300 | Over Budget | 792
Analytics Dashboard | User Acceptance Testing | Olivia Martinez | Low | 2024-09-29 | 2024-11-01 | 2024-11-27 | 100% | 93000 | 104900 | Completed | -11900 | Over Budget | 26
Email Platform Migration | User Acceptance Testing | Priya Patel | Low | 2025-06-06 | 2025-06-13 |  | 0% | 10000 | 0 | Not Started | 10000 | Within Budget | 465
Chatbot Development | Status Reporting | James Wilson | Medium | 2024-07-15 | 2024-08-09 | 2024-08-10 | 100% | 43000 | 39300 | Completed | 3700 | Within Budget | 1
Product Launch Q1 | Stakeholder Interviews | Priya Patel | Low | 2024-01-25 | 2024-02-07 | 2024-03-12 | 100% | 37000 | 45400 | Completed | -8400 | Over Budget | 34
Payment Integration | Change Management | Robert Garcia | Critical | 2024-12-08 | 2025-01-11 | 2025-01-01 | 100% | 69000 | 84000 | Completed | -15000 | Over Budget | -10
Inventory System | Compliance Check | Marcus Johnson | Low | 2024-08-24 | 2024-09-03 |  | 85% | 11000 | 11800 | Delayed | -800 | Over Budget | 748
Compliance Overhaul | Data Migration | Sarah Chen | High | 2025-03-16 | 2025-04-29 |  | 0% | 81000 | 0 | Not Started | 81000 | Within Budget | 510
Product Launch Q1 | Database Design | Hannah White | Medium | 2025-03-17 | 2025-04-24 |  | 0% | 91000 | 0 | Not Started | 91000 | Within Budget | 515
Office Relocation | Stakeholder Interviews | Elena Rodriguez | Medium | 2025-05-02 | 2025-05-09 |  | 0% | 6000 | 0 | Not Started | 6000 | Within Budget | 500
Compliance Overhaul | Competitive Analysis | Rachel Thompson | Medium | 2024-02-23 | 2024-03-04 | 2024-03-05 | 100% | 6000 | 5300 | Completed | 700 | Within Budget | 1
Compliance Overhaul | Status Reporting | Olivia Martinez | High | 2024-11-29 | 2024-12-29 | 2025-01-10 | 100% | 23000 | 20400 | Completed | 2600 | Within Budget | 12
Inventory System | Data Migration | Olivia Martinez | Medium | 2025-06-18 | 2025-08-23 |  | 56% | 190000 | 111800 | In Progress | 78200 | Within Budget | 394
Cloud Infrastructure | A/B Testing Setup | Hannah White | Critical | 2024-08-04 | 2024-09-07 | 2024-09-10 | 100% | 93000 | 93100 | Completed | -100 | Over Budget | 3
API Gateway | Accessibility Audit | Carlos Mendez | High | 2025-01-22 | 2025-02-07 |  | 60% | 47000 | 39200 | Delayed | 7800 | Within Budget | 591
ERP Implementation | Training Materials | Ahmed Hassan | Medium | 2025-03-07 | 2025-03-28 |  | 0% | 20000 | 0 | Not Started | 20000 | Within Budget | 542
Mobile App Launch | Contract Negotiation | Hannah White | Medium | 2024-12-26 | 2025-01-25 |  | 65% | 28000 | 22700 | Delayed | 5300 | Within Budget | 604
Security Audit | Asset Design | Priya Patel | Medium | 2025-01-28 | 2025-02-05 |  | 64% | 7000 | 6300 | Delayed | 700 | Within Budget | 593
Data Warehouse Build | User Training | Lisa Wang | Low | 2025-06-22 | 2025-07-06 |  | 13% | 46000 | 6500 | In Progress | 39500 | Within Budget | 442
Product Launch Q1 | Requirements Gathering | Jessica Turner | High | 2024-02-03 | 2024-02-09 | 2024-02-08 | 100% | 15000 | 18900 | Completed | -3900 | Over Budget | -1
Social Media Revamp | Iteration Planning | Michael Brown | Low | 2025-05-31 | 2025-06-26 |  | 0% | 42000 | 0 | Not Started | 42000 | Within Budget | 452
CRM Migration | Vendor Evaluation | Carlos Mendez | High | 2024-10-23 | 2024-11-06 | 2024-11-24 | 100% | 31000 | 37000 | Completed | -6000 | Over Budget | 18
Email Platform Migration | Vendor Evaluation | Priya Patel | High | 2024-03-09 | 2024-03-25 | 2024-04-13 | 100% | 38000 | 42100 | Completed | -4100 | Over Budget | 19
Supply Chain Optimization | Asset Design | Priya Patel | Low | 2025-05-27 | 2025-06-27 |  | 0% | 64000 | 0 | Not Started | 64000 | Within Budget | 451
Customer Portal | Post-Launch Review | Natasha Singh | Medium | 2024-05-31 | 2024-06-26 | 2024-06-27 | 100% | 14000 | 19400 | Completed | -5400 | Over Budget | 1
Customer Portal | Unit Testing | Emily Davis | Critical | 2024-12-28 | 2025-01-08 | 2025-01-12 | 100% | 24000 | 26900 | Completed | -2900 | Over Budget | 4
Cloud Infrastructure | SEO Optimization | David Kim | High | 2024-03-10 | 2024-03-25 | 2024-03-29 | 100% | 21000 | 28400 | Completed | -7400 | Over Budget | 4
Payment Integration | Backend Development | Elena Rodriguez | High | 2025-02-12 | 2025-04-01 |  | 0% | 42000 | 0 | Not Started | 42000 | Within Budget | 538
Brand Refresh | SEO Optimization | Brian Taylor | Medium | 2024-08-20 | 2024-09-22 | 2024-11-06 | 100% | 94000 | 91600 | Completed | 2400 | Within Budget | 45
Budget Planning Tool | Performance Testing | Rachel Thompson | High | 2024-02-15 | 2024-03-21 | 2024-04-16 | 100% | 73000 | 69400 | Completed | 3600 | Within Budget | 26
HR System Upgrade | Asset Design | Amanda Foster | Medium | 2024-08-23 | 2024-09-03 | 2024-08-28 | 100% | 37000 | 37900 | Completed | -900 | Over Budget | -6
Data Warehouse Build | Feedback Collection | James Wilson | High | 2024-03-11 | 2024-03-25 | 2024-03-16 | 0% | 48000 | 18400 | Cancelled | 29600 | Within Budget | -9
Office Relocation | Frontend Development | Kevin O'Brien | High | 2024-10-26 | 2024-11-25 | 2024-12-15 | 100% | 15000 | 13600 | Completed | 1400 | Within Budget | 20
Product Launch Q1 | UI/UX Design | Carlos Mendez | Critical | 2025-01-16 | 2025-02-13 |  | 92% | 49000 | 49700 | In Progress | -700 | Over Budget | 585
Email Platform Migration | Backend Development | Chris Evans | Low | 2024-08-03 | 2024-10-13 | 2024-11-27 | 100% | 128000 | 146700 | Completed | -18700 | Over Budget | 45
Annual Report | Requirements Gathering | Priya Patel | Critical | 2024-03-20 | 2024-04-03 | 2024-04-01 | 100% | 27000 | 27300 | Completed | -300 | Over Budget | -2
HR System Upgrade | Go-Live Preparation | Sarah Chen | Medium | 2024-09-14 | 2024-09-28 | 2024-10-01 | 100% | 43000 | 36800 | Completed | 6200 | Within Budget | 3
Vendor Portal | Competitive Analysis | Tom Mitchell | High | 2024-03-25 | 2024-04-23 | 2024-05-12 | 100% | 31000 | 37100 | Completed | -6100 | Over Budget | 19
Compliance Overhaul | Database Design | Robert Garcia | High | 2024-02-13 | 2024-03-19 |  | 20% | 46000 | 51200 | Delayed | -5200 | Over Budget | 916
Cloud Infrastructure | Feedback Collection | Stephanie Adams | Medium | 2024-05-15 | 2024-06-19 | 2024-06-29 | 100% | 32000 | 42800 | Completed | -10800 | Over Budget | 10
Email Platform Migration | Bug Fixes | Lisa Wang | Medium | 2024-10-19 | 2024-11-20 | 2024-10-27 | 20% | 58000 | 4400 | Cancelled | 53600 | Within Budget | -24
Inventory System | Code Review | Carlos Mendez | Low | 2025-04-01 | 2025-04-23 |  | 72% | 44000 | 26200 | In Progress | 17800 | Within Budget | 516
API Gateway | Communication Plan | Carlos Mendez | Medium | 2024-09-09 | 2024-10-10 | 2024-10-01 | 100% | 75000 | 91900 | Completed | -16900 | Over Budget | -9
Product Launch Q2 | Analytics Integration | Robert Garcia | High | 2024-04-23 | 2024-05-01 | 2024-05-02 | 100% | 8000 | 7500 | Completed | 500 | Within Budget | 1
Data Warehouse Build | Change Management | Priya Patel | High | 2024-01-20 | 2024-01-30 | 2024-02-03 | 100% | 14000 | 12600 | Completed | 1400 | Within Budget | 4
Website Redesign | Contract Negotiation | Jennifer Lee | Low | 2024-05-05 | 2024-06-06 |  | 35% | 33000 | 29200 | Delayed | 3800 | Within Budget | 837
Cloud Infrastructure | Retrospective | Marcus Johnson | High | 2024-11-20 | 2024-11-30 | 2024-11-22 | 30% | 9000 | 600 | Cancelled | 8400 | Within Budget | -8
Onboarding Automation | Requirements Gathering | Brian Taylor | Low | 2024-11-22 | 2024-12-07 | 2024-12-07 | 100% | 24000 | 23000 | Completed | 1000 | Within Budget | 0
Payment Integration | Post-Launch Review | Natasha Singh | High | 2024-06-17 | 2024-06-28 | 2024-08-07 | 100% | 29000 | 34700 | Completed | -5700 | Over Budget | 40
Marketing Automation | Budget Review | David Kim | High | 2025-03-24 | 2025-04-10 |  | 0% | 34000 | 0 | Not Started | 34000 | Within Budget | 529
Budget Planning Tool | Quality Assurance | Sarah Chen | Low | 2025-04-15 | 2025-05-08 |  | 48% | 33000 | 16100 | In Progress | 16900 | Within Budget | 501
Marketing Automation | Analytics Integration | Michael Brown | Low | 2025-04-27 | 2025-05-26 |  | 16% | 30000 | 4200 | In Progress | 25800 | Within Budget | 483
HR System Upgrade | Compliance Check | Ahmed Hassan | Low | 2024-06-11 | 2024-07-05 | 2024-07-23 | 100% | 37000 | 35600 | Completed | 1400 | Within Budget | 18
Product Launch Q1 | Quality Assurance | Hannah White | Critical | 2024-06-14 | 2024-07-11 | 2024-07-15 | 100% | 50000 | 51100 | Completed | -1100 | Over Budget | 4
Data Warehouse Build | UI/UX Design | Brian Taylor | Low | 2024-10-15 | 2024-11-09 | 2024-12-21 | 100% | 46000 | 56200 | Completed | -10200 | Over Budget | 42
Data Warehouse Build | Vendor Evaluation | Stephanie Adams | Medium | 2024-02-29 | 2024-03-30 | 2024-03-24 | 100% | 38000 | 44800 | Completed | -6800 | Over Budget | -6
Payment Integration | Requirements Gathering | Stephanie Adams | Medium | 2024-12-20 | 2025-01-01 | 2025-01-09 | 100% | 15000 | 20900 | Completed | -5900 | Over Budget | 8
DevOps Pipeline | Stakeholder Interviews | Lisa Wang | Critical | 2024-08-06 | 2024-08-12 | 2024-09-25 | 100% | 9000 | 8100 | Completed | 900 | Within Budget | 44
Website Redesign | User Acceptance Testing | Chris Evans | Medium | 2024-11-18 | 2024-12-04 | 2024-12-22 | 100% | 22000 | 30600 | Completed | -8600 | Over Budget | 18
Product Launch Q2 | Analytics Integration | Kevin O'Brien | Low | 2024-02-21 | 2024-02-28 | 2024-03-23 | 100% | 11000 | 11900 | Completed | -900 | Over Budget | 24
Security Audit | Status Reporting | Chris Evans | Medium | 2025-05-27 | 2025-06-06 |  | 0% | 5000 | 0 | Not Started | 5000 | Within Budget | 472
Training Platform | Bug Fixes | Olivia Martinez | Medium | 2024-02-25 | 2024-03-25 |  | 62% | 47000 | 27900 | Delayed | 19100 | Within Budget | 910
Cloud Infrastructure | Performance Testing | Natasha Singh | High | 2024-09-18 | 2024-09-27 |  | 56% | 12000 | 8700 | Delayed | 3300 | Within Budget | 724
Website Redesign | Asset Design | Carlos Mendez | High | 2024-01-21 | 2024-01-30 |  | 63% | 7000 | 5900 | Delayed | 1100 | Within Budget | 965
Customer Portal | Data Migration | Emily Davis | High | 2024-10-14 | 2024-11-21 | 2024-11-29 | 100% | 42000 | 44400 | Completed | -2400 | Over Budget | 8
Security Audit | Security Review | Jessica Turner | Critical | 2025-03-21 | 2025-04-02 |  | 0% | 20000 | 0 | Not Started | 20000 | Within Budget | 537
Security Audit | Budget Review | Jennifer Lee | Low | 2024-11-15 | 2024-12-17 | 2024-12-17 | 100% | 79000 | 105900 | Completed | -26900 | Over Budget | 0
DevOps Pipeline | Asset Design | Ahmed Hassan | High | 2025-01-18 | 2025-02-09 | 2025-02-27 | 100% | 49000 | 51700 | Completed | -2700 | Over Budget | 18
Brand Refresh | Bug Fixes | Emily Davis | Low | 2025-03-08 | 2025-04-07 |  | 14% | 40000 | 6200 | In Progress | 33800 | Within Budget | 532
Budget Planning Tool | Risk Assessment | Elena Rodriguez | High | 2025-03-12 | 2025-03-29 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 541
Payment Integration | Go-Live Preparation | Marcus Johnson | Critical | 2025-01-24 | 2025-02-11 |  | 23% | 38000 | 29900 | Delayed | 8100 | Within Budget | 587
Email Platform Migration | Technical Architecture | Amanda Foster | High | 2025-05-09 | 2025-06-01 |  | 0% | 40000 | 0 | Not Started | 40000 | Within Budget | 477
Customer Portal | System Configuration | Stephanie Adams | Critical | 2024-07-13 | 2024-08-07 | 2024-09-02 | 100% | 15000 | 14600 | Completed | 400 | Within Budget | 26
Customer Portal | Competitive Analysis | Natasha Singh | High | 2025-01-17 | 2025-02-06 |  | 25% | 43000 | 11700 | In Progress | 31300 | Within Budget | 592
Supply Chain Optimization | Retrospective | Chris Evans | High | 2024-06-03 | 2024-06-13 | 2024-06-25 | 100% | 15000 | 13800 | Completed | 1200 | Within Budget | 12
Supply Chain Optimization | Budget Review | Elena Rodriguez | Medium | 2024-06-19 | 2024-07-04 | 2024-07-05 | 100% | 10000 | 12300 | Completed | -2300 | Over Budget | 1
Social Media Revamp | Performance Testing | Michael Brown | Medium | 2024-02-03 | 2024-03-07 | 2024-03-08 | 100% | 95000 | 96300 | Completed | -1300 | Over Budget | 1
Email Platform Migration | A/B Testing Setup | Brian Taylor | High | 2025-03-03 | 2025-03-26 |  | 0% | 46000 | 0 | Not Started | 46000 | Within Budget | 544
Training Platform | Unit Testing | David Kim | Low | 2024-07-12 | 2024-07-29 | 2024-07-31 | 100% | 21000 | 25600 | Completed | -4600 | Over Budget | 2
Product Launch Q1 | Security Review | Kevin O'Brien | Medium | 2025-04-14 | 2025-05-10 |  | 10% | 43000 | 4300 | In Progress | 38700 | Within Budget | 499
API Gateway | SEO Optimization | Olivia Martinez | Medium | 2024-01-17 | 2024-01-31 | 2024-01-22 | 15% | 48000 | 10200 | Cancelled | 37800 | Within Budget | -9
Inventory System | Asset Design | Jennifer Lee | Medium | 2024-10-06 | 2024-10-21 | 2024-10-07 | 0% | 31000 | 10600 | Cancelled | 20400 | Within Budget | -14
API Gateway | Quality Assurance | Stephanie Adams | Critical | 2024-09-22 | 2024-10-27 | 2024-12-03 | 100% | 89000 | 101700 | Completed | -12700 | Over Budget | 37
Training Platform | Competitive Analysis | Priya Patel | Medium | 2024-04-20 | 2024-05-22 | 2024-04-28 | 0% | 67000 | 9100 | Cancelled | 57900 | Within Budget | -24
Marketing Automation | Backend Development | Daniel Park | Medium | 2024-07-31 | 2024-10-29 | 2024-12-09 | 100% | 175000 | 148800 | Completed | 26200 | Within Budget | 41
CRM Migration | Communication Plan | Stephanie Adams | Low | 2024-02-29 | 2024-03-16 | 2024-03-04 | 10% | 13000 | 2900 | Cancelled | 10100 | Within Budget | -12
ERP Implementation | Status Reporting | Elena Rodriguez | Low | 2024-03-01 | 2024-03-17 |  | 55% | 31000 | 19100 | Delayed | 11900 | Within Budget | 918
Product Launch Q2 | Accessibility Audit | James Wilson | High | 2024-12-10 | 2024-12-26 | 2024-12-12 | 25% | 23000 | 8200 | Cancelled | 14800 | Within Budget | -14
ERP Implementation | Sprint Planning | Tom Mitchell | High | 2025-06-22 | 2025-07-05 |  | 0% | 22000 | 0 | Not Started | 22000 | Within Budget | 443
Marketing Automation | Technical Architecture | Marcus Johnson | Critical | 2025-06-07 | 2025-06-17 |  | 0% | 13000 | 0 | Not Started | 13000 | Within Budget | 461
Training Platform | Feedback Collection | Carlos Mendez | High | 2024-12-19 | 2025-01-13 |  | 43% | 24000 | 10200 | On Hold | 13800 | Within Budget | 616
CRM Migration | Contract Negotiation | James Wilson | High | 2025-01-15 | 2025-02-02 | 2025-02-22 | 100% | 13000 | 11200 | Completed | 1800 | Within Budget | 20
Mobile App Launch | Accessibility Audit | Ahmed Hassan | Critical | 2025-06-25 | 2025-07-23 |  | 0% | 37000 | 0 | Not Started | 37000 | Within Budget | 425
Training Platform | Backend Development | Marcus Johnson | High | 2024-11-27 | 2025-02-15 |  | 69% | 107000 | 22200 | On Hold | 84800 | Within Budget | 583
Product Launch Q2 | Bug Fixes | Brian Taylor | Medium | 2025-03-02 | 2025-04-06 |  | 23% | 73000 | 20100 | In Progress | 52900 | Within Budget | 533
Payment Integration | UI/UX Design | Daniel Park | High | 2024-01-18 | 2024-02-07 | 2024-02-17 | 100% | 32000 | 40100 | Completed | -8100 | Over Budget | 10
Brand Refresh | Status Reporting | Jessica Turner | Medium | 2025-02-17 | 2025-03-12 |  | 70% | 36000 | 21200 | In Progress | 14800 | Within Budget | 558
Social Media Revamp | User Acceptance Testing | Olivia Martinez | Low | 2024-09-04 | 2024-09-26 | 2024-09-08 | 30% | 23000 | 6600 | Cancelled | 16400 | Within Budget | -18
Chatbot Development | User Training | Stephanie Adams | Medium | 2024-06-11 | 2024-07-15 | 2024-07-19 | 100% | 47000 | 41100 | Completed | 5900 | Within Budget | 4
Product Launch Q2 | Performance Testing | Tom Mitchell | Medium | 2024-05-02 | 2024-05-30 |  | 78% | 18000 | 12600 | Delayed | 5400 | Within Budget | 844
HR System Upgrade | Documentation | Brian Taylor | High | 2025-06-14 | 2025-07-19 |  | 0% | 74000 | 0 | Not Started | 74000 | Within Budget | 429
Supply Chain Optimization | Frontend Development | Amanda Foster | Medium | 2025-03-25 | 2025-04-24 |  | 0% | 35000 | 0 | Not Started | 35000 | Within Budget | 515
DevOps Pipeline | Risk Assessment | Lisa Wang | High | 2025-02-12 | 2025-02-22 | 2025-03-13 | 100% | 6000 | 5900 | Completed | 100 | Within Budget | 19
Brand Refresh | Budget Review | Emily Davis | Low | 2024-01-07 | 2024-02-08 | 2024-03-06 | 100% | 46000 | 50000 | Completed | -4000 | Over Budget | 27
Social Media Revamp | Change Management | Hannah White | Medium | 2024-09-12 | 2024-10-12 | 2024-10-19 | 100% | 40000 | 42100 | Completed | -2100 | Over Budget | 7
Performance Review System | Asset Design | Sarah Chen | Medium | 2024-02-17 | 2024-03-03 | 2024-03-16 | 100% | 23000 | 24000 | Completed | -1000 | Over Budget | 13
Performance Review System | Accessibility Audit | Daniel Park | Low | 2025-02-04 | 2025-03-02 |  | 31% | 42000 | 14300 | In Progress | 27700 | Within Budget | 568
Inventory System | Monitoring Setup | Daniel Park | Medium | 2025-03-08 | 2025-04-02 |  | 43% | 20000 | 9700 | In Progress | 10300 | Within Budget | 537
Office Relocation | Risk Assessment | Jennifer Lee | Medium | 2024-07-03 | 2024-07-21 | 2024-07-12 | 100% | 49000 | 55800 | Completed | -6800 | Over Budget | -9
Inventory System | Quality Assurance | Sarah Chen | Low | 2024-07-09 | 2024-08-09 | 2024-07-19 | 30% | 91000 | 25700 | Cancelled | 65300 | Within Budget | -21
API Gateway | Budget Review | Ahmed Hassan | High | 2024-09-10 | 2024-10-01 |  | 82% | 12000 | 8900 | Delayed | 3100 | Within Budget | 720
Payment Integration | SEO Optimization | Stephanie Adams | Critical | 2024-12-06 | 2024-12-28 | 2024-12-17 | 15% | 20000 | 7800 | Cancelled | 12200 | Within Budget | -11
Marketing Automation | Communication Plan | Robert Garcia | Medium | 2024-08-17 | 2024-09-07 | 2024-09-04 | 100% | 17000 | 20300 | Completed | -3300 | Over Budget | -3
Marketing Automation | Go-Live Preparation | Jennifer Lee | High | 2024-02-09 | 2024-02-17 | 2024-02-13 | 25% | 4000 | 1000 | Cancelled | 3000 | Within Budget | -4
Onboarding Automation | Iteration Planning | Carlos Mendez | Low | 2025-04-08 | 2025-05-09 |  | 0% | 92000 | 0 | Not Started | 92000 | Within Budget | 500
ERP Implementation | Contract Negotiation | Jessica Turner | High | 2025-06-25 | 2025-07-22 |  | 0% | 21000 | 0 | Not Started | 21000 | Within Budget | 426
Compliance Overhaul | Analytics Integration | Chris Evans | Critical | 2024-09-07 | 2024-10-10 | 2024-10-23 | 100% | 49000 | 60600 | Completed | -11600 | Over Budget | 13
Performance Review System | Status Reporting | Michael Brown | Medium | 2024-07-20 | 2024-07-30 | 2024-07-30 | 100% | 11000 | 12500 | Completed | -1500 | Over Budget | 0
Performance Review System | System Configuration | Rachel Thompson | Low | 2025-05-13 | 2025-05-23 |  | 0% | 8000 | 0 | Not Started | 8000 | Within Budget | 486
Training Platform | Post-Launch Review | Carlos Mendez | High | 2024-08-08 | 2024-08-25 | 2024-08-30 | 100% | 31000 | 36700 | Completed | -5700 | Over Budget | 5
Compliance Overhaul | Database Design | Rachel Thompson | Low | 2024-11-08 | 2024-12-21 |  | 47% | 62000 | 68300 | Delayed | -6300 | Over Budget | 639
Budget Planning Tool | Communication Plan | Jennifer Lee | High | 2024-08-08 | 2024-08-27 | 2024-09-08 | 100% | 14000 | 14200 | Completed | -200 | Over Budget | 12
Marketing Automation | Frontend Development | Marcus Johnson | Low | 2024-05-14 | 2024-08-10 |  | 67% | 193000 | 146200 | Delayed | 46800 | Within Budget | 772
Customer Portal | Data Migration | Priya Patel | Low | 2024-08-05 | 2024-10-24 | 2024-11-30 | 100% | 150000 | 168500 | Completed | -18500 | Over Budget | 37
Compliance Overhaul | Security Review | Tom Mitchell | High | 2024-09-12 | 2024-09-20 | 2024-09-20 | 100% | 13000 | 17200 | Completed | -4200 | Over Budget | 0
CRM Migration | Communication Plan | Jessica Turner | Critical | 2024-12-21 | 2025-01-19 |  | 83% | 33000 | 26000 | In Progress | 7000 | Within Budget | 610
Brand Refresh | Communication Plan | Rachel Thompson | Low | 2024-01-14 | 2024-02-16 | 2024-03-04 | 100% | 47000 | 50800 | Completed | -3800 | Over Budget | 17
Inventory System | Optimization | David Kim | High | 2024-03-20 | 2024-03-28 | 2024-04-13 | 100% | 7000 | 9200 | Completed | -2200 | Over Budget | 16
Vendor Portal | Database Design | Carlos Mendez | High | 2024-03-07 | 2024-04-04 | 2024-04-04 | 100% | 12000 | 16200 | Completed | -4200 | Over Budget | 0
Supply Chain Optimization | API Development | Daniel Park | Medium | 2024-02-11 | 2024-03-14 | 2024-03-31 | 100% | 83000 | 83300 | Completed | -300 | Over Budget | 17
API Gateway | Risk Assessment | Daniel Park | Medium | 2024-07-22 | 2024-08-16 | 2024-08-28 | 100% | 29000 | 25800 | Completed | 3200 | Within Budget | 12
Annual Report | Documentation | Sarah Chen | Medium | 2025-03-16 | 2025-03-29 |  | 0% | 39000 | 0 | Not Started | 39000 | Within Budget | 541
CRM Migration | Competitive Analysis | Tom Mitchell | Low | 2024-08-30 | 2024-10-02 | 2024-10-10 | 100% | 91000 | 112700 | Completed | -21700 | Over Budget | 8
Analytics Dashboard | Market Research | Tom Mitchell | Medium | 2024-01-16 | 2024-01-31 | 2024-03-07 | 100% | 43000 | 51600 | Completed | -8600 | Over Budget | 36
Compliance Overhaul | User Training | Sarah Chen | Low | 2024-08-20 | 2024-09-17 | 2024-09-17 | 100% | 32000 | 41100 | Completed | -9100 | Over Budget | 0
Payment Integration | Wireframing | Jessica Turner | Medium | 2025-02-07 | 2025-03-14 |  | 18% | 68000 | 13200 | In Progress | 54800 | Within Budget | 556
Social Media Revamp | Competitive Analysis | Robert Garcia | Low | 2024-12-26 | 2025-01-26 |  | 80% | 83000 | 46400 | Delayed | 36600 | Within Budget | 603
Brand Refresh | System Configuration | David Kim | Low | 2024-04-08 | 2024-04-29 |  | 41% | 34000 | 34900 | Delayed | -900 | Over Budget | 875
Product Launch Q2 | Technical Architecture | Ahmed Hassan | Low | 2024-09-11 | 2024-09-21 | 2024-10-08 | 100% | 11000 | 11000 | Completed | 0 | Within Budget | 17
Analytics Dashboard | A/B Testing Setup | James Wilson | Medium | 2024-09-29 | 2024-10-18 | 2024-11-02 | 100% | 32000 | 37000 | Completed | -5000 | Over Budget | 15
Marketing Automation | Sprint Planning | Elena Rodriguez | High | 2024-07-04 | 2024-07-19 |  | 58% | 29000 | 21000 | Delayed | 8000 | Within Budget | 794
Compliance Overhaul | User Training | Amanda Foster | Low | 2024-07-07 | 2024-07-21 | 2024-07-25 | 100% | 30000 | 25900 | Completed | 4100 | Within Budget | 4
Chatbot Development | Budget Review | Marcus Johnson | High | 2024-07-04 | 2024-07-23 | 2024-07-17 | 100% | 25000 | 21600 | Completed | 3400 | Within Budget | -6
Onboarding Automation | Post-Launch Review | Tom Mitchell | Low | 2024-07-25 | 2024-08-23 |  | 61% | 19000 | 23900 | Delayed | -4900 | Over Budget | 759
Office Relocation | API Development | Olivia Martinez | Medium | 2025-01-22 | 2025-01-30 | 2025-02-26 | 100% | 4000 | 4400 | Completed | -400 | Over Budget | 27
Website Redesign | Backup Configuration | Hannah White | Low | 2024-05-14 | 2024-06-14 | 2024-06-24 | 100% | 51000 | 43900 | Completed | 7100 | Within Budget | 10
Training Platform | Performance Testing | Amanda Foster | Low | 2025-05-30 | 2025-06-15 |  | 39% | 23000 | 9300 | In Progress | 13700 | Within Budget | 463
Chatbot Development | Market Research | Kevin O'Brien | Medium | 2025-05-08 | 2025-05-20 |  | 0% | 33000 | 0 | Not Started | 33000 | Within Budget | 489
Supply Chain Optimization | User Training | Tom Mitchell | Medium | 2024-05-08 | 2024-05-19 | 2024-05-09 | 25% | 18000 | 2200 | Cancelled | 15800 | Within Budget | -10
Onboarding Automation | Security Review | Chris Evans | Medium | 2024-06-12 | 2024-06-30 | 2024-07-10 | 100% | 46000 | 59800 | Completed | -13800 | Over Budget | 10
API Gateway | Market Research | Daniel Park | Medium | 2024-11-19 | 2024-11-29 | 2024-12-17 | 100% | 12000 | 10400 | Completed | 1600 | Within Budget | 18
Email Platform Migration | Asset Design | Rachel Thompson | Medium | 2024-04-03 | 2024-04-29 | 2024-05-25 | 100% | 37000 | 33600 | Completed | 3400 | Within Budget | 26
Onboarding Automation | Training Materials | Daniel Park | Medium | 2024-10-13 | 2024-11-15 |  | 57% | 40000 | 31500 | Delayed | 8500 | Within Budget | 675
Product Launch Q2 | Quality Assurance | Robert Garcia | Critical | 2025-04-01 | 2025-04-16 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 523
Analytics Dashboard | Quality Assurance | David Kim | Low | 2025-06-22 | 2025-07-17 |  | 27% | 15000 | 3300 | In Progress | 11700 | Within Budget | 431
Product Launch Q1 | Analytics Integration | Olivia Martinez | High | 2025-02-11 | 2025-03-16 |  | 36% | 61000 | 22300 | In Progress | 38700 | Within Budget | 554
Payment Integration | Deployment Planning | Tom Mitchell | Medium | 2025-02-12 | 2025-02-22 | 2025-02-14 | 100% | 4000 | 3800 | Completed | 200 | Within Budget | -8
Product Launch Q1 | Feedback Collection | Hannah White | Low | 2024-09-05 | 2024-10-02 | 2024-10-16 | 100% | 46000 | 46200 | Completed | -200 | Over Budget | 14
Social Media Revamp | Vendor Evaluation | Daniel Park | Low | 2024-01-25 | 2024-02-02 |  | 67% | 10000 | 9500 | Delayed | 500 | Within Budget | 962
Social Media Revamp | Requirements Gathering | James Wilson | Medium | 2024-11-22 | 2024-12-02 | 2024-11-24 | 100% | 9000 | 11300 | Completed | -2300 | Over Budget | -8
Social Media Revamp | Infrastructure Setup | Ahmed Hassan | High | 2024-02-01 | 2024-02-13 | 2024-03-13 | 100% | 37000 | 49600 | Completed | -12600 | Over Budget | 29
Product Launch Q2 | Go-Live Preparation | Amanda Foster | Low | 2024-03-22 | 2024-04-11 | 2024-04-22 | 100% | 16000 | 20500 | Completed | -4500 | Over Budget | 11
Payment Integration | UI/UX Design | David Kim | Medium | 2025-05-13 | 2025-05-29 |  | 0% | 36000 | 0 | Not Started | 36000 | Within Budget | 480
Inventory System | Risk Assessment | Brian Taylor | Medium | 2025-05-03 | 2025-05-28 |  | 0% | 47000 | 0 | Not Started | 47000 | Within Budget | 481
Performance Review System | UI/UX Design | Ahmed Hassan | High | 2024-11-11 | 2024-12-04 |  | 42% | 20000 | 15100 | Delayed | 4900 | Within Budget | 656
Performance Review System | User Acceptance Testing | Robert Garcia | High | 2024-10-24 | 2024-11-22 | 2024-11-22 | 100% | 38000 | 32600 | Completed | 5400 | Within Budget | 0
Product Launch Q1 | Post-Launch Review | Lisa Wang | High | 2025-03-31 | 2025-04-14 |  | 0% | 37000 | 0 | Not Started | 37000 | Within Budget | 525
Compliance Overhaul | Accessibility Audit | Hannah White | Critical | 2024-05-31 | 2024-06-09 | 2024-06-04 | 30% | 4000 | 1000 | Cancelled | 3000 | Within Budget | -5
Social Media Revamp | Communication Plan | Jessica Turner | High | 2024-07-30 | 2024-08-16 | 2024-08-11 | 100% | 41000 | 43000 | Completed | -2000 | Over Budget | -5
Email Platform Migration | Security Review | Priya Patel | High | 2024-11-02 | 2024-11-18 | 2024-11-10 | 30% | 42000 | 4600 | Cancelled | 37400 | Within Budget | -8
Security Audit | Go-Live Preparation | James Wilson | Low | 2024-11-03 | 2024-11-30 | 2025-01-12 | 100% | 37000 | 34400 | Completed | 2600 | Within Budget | 43
HR System Upgrade | Compliance Check | Ahmed Hassan | High | 2024-09-28 | 2024-10-23 |  | 81% | 46000 | 58800 | Delayed | -12800 | Over Budget | 698
Security Audit | Risk Assessment | Carlos Mendez | Critical | 2025-06-23 | 2025-07-01 |  | 48% | 4000 | 1800 | In Progress | 2200 | Within Budget | 447
Supply Chain Optimization | Backend Development | Stephanie Adams | Medium | 2025-06-10 | 2025-08-09 |  | 0% | 83000 | 0 | Not Started | 83000 | Within Budget | 408
Social Media Revamp | Performance Testing | Marcus Johnson | High | 2024-12-28 | 2025-01-24 | 2025-03-10 | 100% | 21000 | 22500 | Completed | -1500 | Over Budget | 45
Cloud Infrastructure | User Training | Kevin O'Brien | Medium | 2024-10-06 | 2024-10-29 | 2024-11-09 | 100% | 49000 | 66100 | Completed | -17100 | Over Budget | 11
Payment Integration | Accessibility Audit | Natasha Singh | Medium | 2025-06-17 | 2025-07-08 |  | 0% | 13000 | 0 | Not Started | 13000 | Within Budget | 440
Onboarding Automation | Prototype Development | Robert Garcia | Low | 2025-03-12 | 2025-04-12 |  | 74% | 45000 | 29200 | In Progress | 15800 | Within Budget | 527
Marketing Automation | Deployment Planning | Jennifer Lee | Medium | 2025-03-22 | 2025-04-18 |  | 0% | 39000 | 0 | Not Started | 39000 | Within Budget | 521
HR System Upgrade | System Configuration | Natasha Singh | Critical | 2024-12-28 | 2025-01-29 | 2025-02-14 | 100% | 37000 | 42500 | Completed | -5500 | Over Budget | 16
Cloud Infrastructure | Monitoring Setup | Tom Mitchell | Medium | 2024-08-15 | 2024-09-04 |  | 41% | 20000 | 19700 | Delayed | 300 | Within Budget | 747
Office Relocation | Change Management | Elena Rodriguez | High | 2024-05-22 | 2024-06-08 | 2024-06-08 | 100% | 31000 | 37800 | Completed | -6800 | Over Budget | 0
Budget Planning Tool | A/B Testing Setup | Hannah White | Critical | 2024-02-24 | 2024-03-17 | 2024-03-17 | 100% | 46000 | 44300 | Completed | 1700 | Within Budget | 0
Email Platform Migration | Requirements Gathering | Chris Evans | High | 2024-12-20 | 2024-12-27 |  | 35% | 5000 | 5700 | Delayed | -700 | Over Budget | 633
Brand Refresh | Post-Launch Review | Priya Patel | Medium | 2024-09-03 | 2024-09-13 |  | 85% | 15000 | 8500 | Delayed | 6500 | Within Budget | 738
Annual Report | Sprint Planning | Rachel Thompson | Low | 2024-09-04 | 2024-09-12 |  | 31% | 6000 | 3500 | Delayed | 2500 | Within Budget | 739
Analytics Dashboard | Change Management | David Kim | Low | 2025-04-28 | 2025-05-14 |  | 40% | 29000 | 10200 | In Progress | 18800 | Within Budget | 495
Inventory System | System Configuration | Olivia Martinez | Medium | 2024-11-18 | 2024-12-23 |  | 51% | 67000 | 74100 | Delayed | -7100 | Over Budget | 637
Annual Report | Infrastructure Setup | Rachel Thompson | Medium | 2025-03-24 | 2025-04-13 |  | 56% | 42000 | 22500 | In Progress | 19500 | Within Budget | 526
Marketing Automation | Status Reporting | Robert Garcia | Critical | 2025-02-19 | 2025-03-16 |  | 40% | 38000 | 15600 | In Progress | 22400 | Within Budget | 554
DevOps Pipeline | Wireframing | Tom Mitchell | Low | 2024-04-01 | 2024-05-04 | 2024-05-04 | 100% | 64000 | 72100 | Completed | -8100 | Over Budget | 0
Inventory System | Budget Review | Tom Mitchell | High | 2024-06-12 | 2024-06-27 | 2024-07-06 | 100% | 25000 | 32200 | Completed | -7200 | Over Budget | 9
Inventory System | Technical Architecture | James Wilson | Low | 2025-02-26 | 2025-03-23 |  | 87% | 33000 | 32500 | In Progress | 500 | Within Budget | 547
Website Redesign | Risk Assessment | Hannah White | Medium | 2024-06-21 | 2024-07-10 | 2024-07-15 | 100% | 36000 | 32300 | Completed | 3700 | Within Budget | 5
DevOps Pipeline | Unit Testing | Chris Evans | Medium | 2024-09-24 | 2024-10-11 | 2024-10-05 | 100% | 34000 | 42500 | Completed | -8500 | Over Budget | -6
Email Platform Migration | Sprint Planning | Robert Garcia | High | 2024-09-22 | 2024-09-28 | 2024-09-18 | 100% | 3000 | 3200 | Completed | -200 | Over Budget | -10
Security Audit | Asset Design | Ahmed Hassan | High | 2024-02-24 | 2024-03-10 | 2024-04-19 | 100% | 15000 | 15000 | Completed | 0 | Within Budget | 40
Product Launch Q2 | Risk Assessment | David Kim | High | 2024-03-21 | 2024-04-16 | 2024-05-16 | 100% | 24000 | 21200 | Completed | 2800 | Within Budget | 30
Chatbot Development | Status Reporting | Jennifer Lee | Medium | 2024-10-01 | 2024-10-12 | 2024-10-06 | 25% | 43000 | 7400 | Cancelled | 35600 | Within Budget | -6
DevOps Pipeline | System Configuration | Brian Taylor | High | 2024-02-02 | 2024-02-09 |  | 31% | 2000 | 2200 | Delayed | -200 | Over Budget | 955
Cloud Infrastructure | Content Creation | Brian Taylor | High | 2024-02-20 | 2024-03-03 | 2024-03-08 | 100% | 41000 | 41800 | Completed | -800 | Over Budget | 5
Product Launch Q1 | Post-Launch Review | Carlos Mendez | Medium | 2024-06-26 | 2024-07-08 | 2024-07-04 | 100% | 13000 | 14200 | Completed | -1200 | Over Budget | -4
API Gateway | Backup Configuration | Stephanie Adams | Medium | 2024-04-30 | 2024-05-22 |  | 53% | 43000 | 29200 | Delayed | 13800 | Within Budget | 852
Performance Review System | Risk Assessment | Jessica Turner | Low | 2024-11-13 | 2024-11-26 | 2024-12-04 | 100% | 30000 | 36000 | Completed | -6000 | Over Budget | 8
API Gateway | Backend Development | Rachel Thompson | Critical | 2024-03-01 | 2024-04-27 | 2024-05-02 | 100% | 51000 | 49600 | Completed | 1400 | Within Budget | 5
Payment Integration | Prototype Development | Tom Mitchell | Low | 2024-10-03 | 2024-11-03 | 2024-12-01 | 100% | 79000 | 68200 | Completed | 10800 | Within Budget | 28
Cloud Infrastructure | Monitoring Setup | Elena Rodriguez | Medium | 2024-03-02 | 2024-03-10 | 2024-03-08 | 100% | 10000 | 8900 | Completed | 1100 | Within Budget | -2
Vendor Portal | Backup Configuration | Brian Taylor | Medium | 2025-04-11 | 2025-04-28 |  | 0% | 45000 | 0 | Not Started | 45000 | Within Budget | 511
Product Launch Q1 | Post-Launch Review | Natasha Singh | Medium | 2024-01-18 | 2024-02-22 | 2024-01-28 | 30% | 90000 | 35200 | Cancelled | 54800 | Within Budget | -25
CRM Migration | Integration Testing | Jessica Turner | High | 2024-12-21 | 2025-01-23 |  | 85% | 66000 | 49400 | Delayed | 16600 | Within Budget | 606
Supply Chain Optimization | Post-Launch Review | Amanda Foster | Medium | 2024-09-29 | 2024-10-10 |  | 33% | 40000 | 27100 | Delayed | 12900 | Within Budget | 711
Data Warehouse Build | API Development | Elena Rodriguez | Medium | 2024-07-22 | 2024-08-22 | 2024-07-25 | 15% | 68000 | 18900 | Cancelled | 49100 | Within Budget | -28
Office Relocation | User Acceptance Testing | Brian Taylor | Medium | 2025-02-04 | 2025-02-14 | 2025-02-19 | 100% | 13000 | 16500 | Completed | -3500 | Over Budget | 5
Vendor Portal | User Training | Amanda Foster | Medium | 2025-02-17 | 2025-03-14 |  | 17% | 13000 | 2200 | In Progress | 10800 | Within Budget | 556
HR System Upgrade | Performance Testing | Marcus Johnson | Low | 2025-06-14 | 2025-07-05 |  | 28% | 47000 | 10800 | In Progress | 36200 | Within Budget | 443
Website Redesign | Post-Launch Review | Stephanie Adams | High | 2025-05-02 | 2025-05-27 |  | 0% | 48000 | 0 | Not Started | 48000 | Within Budget | 482
Compliance Overhaul | Optimization | Priya Patel | Medium | 2024-08-30 | 2024-09-26 | 2024-09-27 | 100% | 19000 | 21600 | Completed | -2600 | Over Budget | 1
Inventory System | Requirements Gathering | Hannah White | High | 2025-01-15 | 2025-01-25 |  | 13% | 15000 | 2200 | On Hold | 12800 | Within Budget | 604
Vendor Portal | Data Migration | Robert Garcia | High | 2024-01-22 | 2024-04-07 | 2024-02-11 | 30% | 67000 | 17800 | Cancelled | 49200 | Within Budget | -56
Data Warehouse Build | Integration Testing | Robert Garcia | Critical | 2024-08-30 | 2024-10-03 | 2024-10-08 | 100% | 72000 | 88400 | Completed | -16400 | Over Budget | 5
Supply Chain Optimization | Vendor Evaluation | James Wilson | Low | 2025-04-27 | 2025-06-01 |  | 0% | 46000 | 0 | Not Started | 46000 | Within Budget | 477
Product Launch Q1 | Sprint Planning | Tom Mitchell | Medium | 2025-03-01 | 2025-03-16 |  | 19% | 50000 | 9900 | In Progress | 40100 | Within Budget | 554
CRM Migration | Compliance Check | Sarah Chen | High | 2024-06-21 | 2024-07-02 | 2024-07-20 | 100% | 19000 | 21400 | Completed | -2400 | Over Budget | 18
Training Platform | A/B Testing Setup | Kevin O'Brien | High | 2024-06-19 | 2024-07-23 | 2024-08-22 | 100% | 70000 | 92800 | Completed | -22800 | Over Budget | 30
Training Platform | Compliance Check | Priya Patel | Critical | 2024-04-01 | 2024-04-28 |  | 38% | 11000 | 12800 | Delayed | -1800 | Over Budget | 876
Customer Portal | Performance Testing | Amanda Foster | Medium | 2024-05-19 | 2024-06-12 | 2024-05-26 | 25% | 20000 | 7000 | Cancelled | 13000 | Within Budget | -17
Website Redesign | UI/UX Design | Daniel Park | Medium | 2024-08-24 | 2024-10-01 | 2024-09-05 | 15% | 58000 | 8000 | Cancelled | 50000 | Within Budget | -26
Cloud Infrastructure | Sprint Planning | Sarah Chen | Critical | 2025-06-14 | 2025-06-21 |  | 0% | 5000 | 0 | Not Started | 5000 | Within Budget | 457
Vendor Portal | Database Design | Amanda Foster | High | 2025-03-23 | 2025-05-07 |  | 0% | 92000 | 0 | Not Started | 92000 | Within Budget | 502
Product Launch Q1 | Data Migration | Jessica Turner | Low | 2024-04-15 | 2024-06-10 | 2024-04-28 | 30% | 52000 | 4500 | Cancelled | 47500 | Within Budget | -43
Chatbot Development | SEO Optimization | Brian Taylor | Medium | 2024-11-28 | 2024-12-17 | 2024-12-17 | 100% | 19000 | 25000 | Completed | -6000 | Over Budget | 0
Supply Chain Optimization | Status Reporting | Stephanie Adams | Medium | 2024-11-26 | 2024-12-07 | 2024-12-02 | 100% | 44000 | 49400 | Completed | -5400 | Over Budget | -5
Brand Refresh | Accessibility Audit | Tom Mitchell | Low | 2024-12-13 | 2024-12-30 | 2025-01-11 | 100% | 49000 | 42400 | Completed | 6600 | Within Budget | 12
Budget Planning Tool | Iteration Planning | David Kim | Medium | 2024-09-16 | 2024-09-29 |  | 84% | 31000 | 17900 | Delayed | 13100 | Within Budget | 722
Security Audit | Sprint Planning | Robert Garcia | Low | 2025-01-13 | 2025-01-19 |  | 36% | 5000 | 4400 | Delayed | 600 | Within Budget | 610
Mobile App Launch | Backend Development | Tom Mitchell | Low | 2024-10-04 | 2024-12-31 |  | 38% | 168000 | 177000 | Delayed | -9000 | Over Budget | 629
Onboarding Automation | Performance Testing | Rachel Thompson | Medium | 2024-06-08 | 2024-06-26 | 2024-06-29 | 100% | 40000 | 46200 | Completed | -6200 | Over Budget | 3
Office Relocation | Training Materials | Olivia Martinez | Low | 2025-05-04 | 2025-05-21 |  | 39% | 25000 | 9700 | In Progress | 15300 | Within Budget | 488
Mobile App Launch | Content Creation | Emily Davis | High | 2024-07-02 | 2024-07-19 | 2024-08-13 | 100% | 18000 | 19700 | Completed | -1700 | Over Budget | 25
Product Launch Q2 | User Training | Ahmed Hassan | Medium | 2024-05-11 | 2024-05-21 | 2024-06-09 | 100% | 8000 | 7400 | Completed | 600 | Within Budget | 19
Product Launch Q2 | UI/UX Design | Olivia Martinez | Medium | 2024-05-09 | 2024-06-09 | 2024-06-20 | 100% | 73000 | 96700 | Completed | -23700 | Over Budget | 11
CRM Migration | Stakeholder Interviews | Chris Evans | Low | 2025-04-15 | 2025-04-28 |  | 0% | 28000 | 0 | Not Started | 28000 | Within Budget | 511
Training Platform | Competitive Analysis | Michael Brown | Low | 2024-04-09 | 2024-04-18 | 2024-04-16 | 100% | 13000 | 13100 | Completed | -100 | Over Budget | -2
Social Media Revamp | Requirements Gathering | David Kim | Medium | 2025-06-04 | 2025-06-09 |  | 49% | 7000 | 4000 | In Progress | 3000 | Within Budget | 469
Customer Portal | Performance Testing | Chris Evans | Critical | 2025-01-02 | 2025-01-30 |  | 57% | 10000 | 5500 | Delayed | 4500 | Within Budget | 599
CRM Migration | Backup Configuration | Sarah Chen | Medium | 2025-02-15 | 2025-03-11 |  | 82% | 24000 | 21500 | In Progress | 2500 | Within Budget | 559
Performance Review System | Post-Launch Review | Emily Davis | Low | 2025-04-23 | 2025-05-02 |  | 0% | 3000 | 0 | Not Started | 3000 | Within Budget | 507
Training Platform | Unit Testing | Daniel Park | Low | 2024-09-26 | 2024-10-16 | 2024-10-26 | 100% | 35000 | 42500 | Completed | -7500 | Over Budget | 10
CRM Migration | Sprint Planning | David Kim | High | 2025-06-09 | 2025-06-19 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 459
Budget Planning Tool | Requirements Gathering | Olivia Martinez | Low | 2025-01-26 | 2025-02-10 | 2025-02-02 | 100% | 39000 | 35800 | Completed | 3200 | Within Budget | -8
Vendor Portal | Competitive Analysis | Tom Mitchell | Low | 2025-04-12 | 2025-05-08 |  | 0% | 16000 | 0 | Not Started | 16000 | Within Budget | 501
DevOps Pipeline | Quality Assurance | Michael Brown | High | 2025-03-28 | 2025-05-01 |  | 95% | 55000 | 51700 | In Progress | 3300 | Within Budget | 508
ERP Implementation | API Development | James Wilson | Medium | 2024-06-03 | 2024-06-23 | 2024-08-06 | 100% | 45000 | 43400 | Completed | 1600 | Within Budget | 44
ERP Implementation | Monitoring Setup | Ahmed Hassan | Medium | 2024-08-01 | 2024-09-03 | 2024-09-03 | 100% | 80000 | 70400 | Completed | 9600 | Within Budget | 0
ERP Implementation | SEO Optimization | Sarah Chen | High | 2024-06-02 | 2024-06-22 | 2024-06-27 | 100% | 16000 | 13700 | Completed | 2300 | Within Budget | 5
Training Platform | A/B Testing Setup | James Wilson | High | 2024-03-26 | 2024-04-26 | 2024-05-31 | 100% | 90000 | 102100 | Completed | -12100 | Over Budget | 35
Inventory System | API Development | Kevin O'Brien | High | 2024-06-07 | 2024-06-14 | 2024-06-14 | 100% | 8000 | 10000 | Completed | -2000 | Over Budget | 0
HR System Upgrade | Iteration Planning | Sarah Chen | Low | 2024-11-06 | 2024-11-15 | 2024-12-01 | 100% | 2000 | 1900 | Completed | 100 | Within Budget | 16
Office Relocation | Compliance Check | Carlos Mendez | Medium | 2025-01-24 | 2025-02-19 |  | 56% | 31000 | 5200 | On Hold | 25800 | Within Budget | 579
Mobile App Launch | Infrastructure Setup | Robert Garcia | Medium | 2025-03-14 | 2025-04-08 |  | 57% | 37000 | 22600 | In Progress | 14400 | Within Budget | 531
Website Redesign | Risk Assessment | Jennifer Lee | Medium | 2024-01-10 | 2024-02-14 |  | 71% | 60000 | 70000 | Delayed | -10000 | Over Budget | 950
Cloud Infrastructure | Change Management | Tom Mitchell | Medium | 2024-04-26 | 2024-05-21 | 2024-06-11 | 100% | 17000 | 14500 | Completed | 2500 | Within Budget | 21
Office Relocation | Market Research | James Wilson | High | 2024-03-07 | 2024-03-12 |  | 65% | 5000 | 4500 | Delayed | 500 | Within Budget | 923
Analytics Dashboard | Integration Testing | Jessica Turner | High | 2024-06-08 | 2024-07-12 | 2024-07-30 | 100% | 74000 | 63200 | Completed | 10800 | Within Budget | 18
Email Platform Migration | Performance Testing | Lisa Wang | Medium | 2024-09-30 | 2024-10-12 | 2024-10-22 | 100% | 10000 | 12200 | Completed | -2200 | Over Budget | 10
Analytics Dashboard | Backend Development | Stephanie Adams | Medium | 2025-03-17 | 2025-04-18 |  | 0% | 75000 | 0 | Not Started | 75000 | Within Budget | 521
Onboarding Automation | Market Research | James Wilson | Critical | 2025-03-31 | 2025-04-12 |  | 18% | 12000 | 1800 | In Progress | 10200 | Within Budget | 527
Supply Chain Optimization | Data Migration | Brian Taylor | Critical | 2024-04-24 | 2024-07-17 | 2024-07-21 | 100% | 156000 | 164300 | Completed | -8300 | Over Budget | 4
Annual Report | Risk Assessment | Stephanie Adams | Low | 2024-06-30 | 2024-08-01 | 2024-07-10 | 0% | 35000 | 4000 | Cancelled | 31000 | Within Budget | -22
Analytics Dashboard | API Development | David Kim | Medium | 2024-05-23 | 2024-05-31 | 2024-05-27 | 100% | 12000 | 12400 | Completed | -400 | Over Budget | -4
Analytics Dashboard | Asset Design | Carlos Mendez | High | 2024-04-30 | 2024-05-13 |  | 21% | 48000 | 42200 | Delayed | 5800 | Within Budget | 861
Training Platform | Asset Design | Priya Patel | Medium | 2024-05-18 | 2024-06-22 |  | 42% | 43000 | 54100 | Delayed | -11100 | Over Budget | 821
Analytics Dashboard | Competitive Analysis | Tom Mitchell | Critical | 2024-07-29 | 2024-08-31 | 2024-08-04 | 0% | 78000 | 31000 | Cancelled | 47000 | Within Budget | -27
API Gateway | User Training | Elena Rodriguez | High | 2024-12-05 | 2024-12-21 | 2024-12-07 | 25% | 41000 | 4600 | Cancelled | 36400 | Within Budget | -14
Training Platform | Backend Development | Michael Brown | Medium | 2024-08-17 | 2024-10-24 | 2024-09-08 | 25% | 118000 | 33800 | Cancelled | 84200 | Within Budget | -46
Chatbot Development | Backend Development | Marcus Johnson | Critical | 2024-10-25 | 2025-01-20 |  | 92% | 175000 | 165700 | In Progress | 9300 | Within Budget | 609
Analytics Dashboard | A/B Testing Setup | Emily Davis | High | 2024-05-06 | 2024-05-25 | 2024-05-10 | 0% | 44000 | 2700 | Cancelled | 41300 | Within Budget | -15
Analytics Dashboard | Post-Launch Review | Rachel Thompson | High | 2024-08-31 | 2024-09-23 | 2024-10-19 | 100% | 21000 | 26200 | Completed | -5200 | Over Budget | 26
Budget Planning Tool | Database Design | Jennifer Lee | Low | 2024-10-27 | 2024-12-06 | 2024-11-02 | 25% | 57000 | 17800 | Cancelled | 39200 | Within Budget | -34
DevOps Pipeline | Sprint Planning | Robert Garcia | Medium | 2025-05-25 | 2025-06-04 |  | 0% | 4000 | 0 | Not Started | 4000 | Within Budget | 474
Cloud Infrastructure | Training Materials | Jessica Turner | Low | 2025-03-27 | 2025-04-15 |  | 74% | 25000 | 21800 | In Progress | 3200 | Within Budget | 524
Budget Planning Tool | Backend Development | Jessica Turner | Medium | 2024-01-16 | 2024-03-02 | 2024-03-31 | 100% | 83000 | 76800 | Completed | 6200 | Within Budget | 29
Customer Portal | Unit Testing | James Wilson | Medium | 2025-04-26 | 2025-05-21 |  | 0% | 40000 | 0 | Not Started | 40000 | Within Budget | 488
Social Media Revamp | Retrospective | Emily Davis | Medium | 2025-02-20 | 2025-03-07 |  | 66% | 49000 | 35400 | Delayed | 13600 | Within Budget | 563
Compliance Overhaul | Sprint Planning | Brian Taylor | High | 2025-04-21 | 2025-04-28 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 511
Onboarding Automation | Frontend Development | Natasha Singh | Medium | 2024-01-26 | 2024-03-29 |  | 23% | 111000 | 133200 | Delayed | -22200 | Over Budget | 906
Training Platform | Change Management | Robert Garcia | Low | 2025-04-18 | 2025-05-10 |  | 80% | 48000 | 31300 | In Progress | 16700 | Within Budget | 499
Product Launch Q2 | Integration Testing | Ahmed Hassan | Medium | 2024-01-02 | 2024-01-27 | 2024-03-08 | 100% | 50000 | 57500 | Completed | -7500 | Over Budget | 41
Website Redesign | Retrospective | Tom Mitchell | High | 2024-05-02 | 2024-05-08 | 2024-05-15 | 100% | 4000 | 4500 | Completed | -500 | Over Budget | 7
Cloud Infrastructure | UI/UX Design | Rachel Thompson | Medium | 2024-06-24 | 2024-07-28 |  | 24% | 89000 | 99500 | Delayed | -10500 | Over Budget | 785
Compliance Overhaul | Frontend Development | Emily Davis | High | 2024-12-29 | 2025-03-03 |  | 62% | 199000 | 28000 | On Hold | 171000 | Within Budget | 567
Supply Chain Optimization | SEO Optimization | Marcus Johnson | Low | 2024-06-17 | 2024-07-18 | 2024-07-26 | 100% | 61000 | 82200 | Completed | -21200 | Over Budget | 8
Annual Report | Data Migration | Jennifer Lee | Low | 2024-05-27 | 2024-07-23 | 2024-07-15 | 100% | 83000 | 105000 | Completed | -22000 | Over Budget | -8
Product Launch Q1 | Sprint Planning | Amanda Foster | Medium | 2024-04-12 | 2024-04-25 | 2024-05-30 | 100% | 41000 | 49900 | Completed | -8900 | Over Budget | 35
CRM Migration | Competitive Analysis | Elena Rodriguez | High | 2024-04-20 | 2024-05-03 |  | 20% | 15000 | 17000 | Delayed | -2000 | Over Budget | 871
CRM Migration | Deployment Planning | Ahmed Hassan | Low | 2024-07-27 | 2024-08-28 | 2024-09-06 | 100% | 68000 | 80200 | Completed | -12200 | Over Budget | 9
Security Audit | Iteration Planning | James Wilson | Medium | 2024-02-28 | 2024-03-16 |  | 71% | 35000 | 18200 | Delayed | 16800 | Within Budget | 919
Social Media Revamp | Security Review | Sarah Chen | Medium | 2025-02-19 | 2025-03-05 |  | 58% | 42000 | 9100 | On Hold | 32900 | Within Budget | 565
Mobile App Launch | Optimization | Natasha Singh | Critical | 2024-06-27 | 2024-07-25 | 2024-07-08 | 25% | 46000 | 11000 | Cancelled | 35000 | Within Budget | -17
Analytics Dashboard | Database Design | Jessica Turner | Critical | 2024-05-27 | 2024-06-25 | 2024-07-29 | 100% | 36000 | 41700 | Completed | -5700 | Over Budget | 34
Email Platform Migration | Asset Design | Priya Patel | High | 2024-02-29 | 2024-04-02 | 2024-03-12 | 0% | 50000 | 10500 | Cancelled | 39500 | Within Budget | -21
Mobile App Launch | Feedback Collection | James Wilson | High | 2024-10-26 | 2024-11-17 | 2024-10-27 | 10% | 22000 | 8600 | Cancelled | 13400 | Within Budget | -21
Payment Integration | Training Materials | Lisa Wang | Medium | 2024-01-04 | 2024-01-14 | 2024-01-14 | 100% | 3000 | 4000 | Completed | -1000 | Over Budget | 0
Product Launch Q2 | Content Creation | Chris Evans | High | 2024-04-09 | 2024-05-02 | 2024-05-07 | 100% | 35000 | 43100 | Completed | -8100 | Over Budget | 5
Payment Integration | User Acceptance Testing | Olivia Martinez | Low | 2024-06-02 | 2024-06-10 | 2024-06-14 | 100% | 4000 | 4700 | Completed | -700 | Over Budget | 4
Performance Review System | Training Materials | Stephanie Adams | Medium | 2024-01-16 | 2024-02-20 |  | 51% | 94000 | 91100 | Delayed | 2900 | Within Budget | 944
Website Redesign | Optimization | Ahmed Hassan | Low | 2024-05-09 | 2024-06-13 | 2024-07-20 | 100% | 95000 | 98600 | Completed | -3600 | Over Budget | 37
Mobile App Launch | Backup Configuration | Hannah White | High | 2024-10-17 | 2024-11-20 | 2024-11-01 | 25% | 57000 | 5600 | Cancelled | 51400 | Within Budget | -19
Product Launch Q2 | Status Reporting | Daniel Park | Low | 2025-04-22 | 2025-05-08 |  | 0% | 12000 | 0 | Not Started | 12000 | Within Budget | 501
Security Audit | User Training | Emily Davis | Medium | 2025-06-21 | 2025-07-14 |  | 0% | 38000 | 0 | Not Started | 38000 | Within Budget | 434
Analytics Dashboard | A/B Testing Setup | Amanda Foster | High | 2024-12-09 | 2025-01-09 | 2025-02-20 | 100% | 72000 | 68400 | Completed | 3600 | Within Budget | 42
Social Media Revamp | Documentation | Jessica Turner | Critical | 2024-05-29 | 2024-06-05 | 2024-06-09 | 100% | 6000 | 7300 | Completed | -1300 | Over Budget | 4
Brand Refresh | Performance Testing | Stephanie Adams | High | 2024-11-12 | 2024-12-01 | 2024-12-15 | 100% | 15000 | 16700 | Completed | -1700 | Over Budget | 14
Inventory System | Bug Fixes | Daniel Park | Medium | 2024-09-03 | 2024-10-07 | 2024-10-20 | 100% | 90000 | 110700 | Completed | -20700 | Over Budget | 13
Payment Integration | Backup Configuration | Natasha Singh | High | 2025-02-07 | 2025-02-14 |  | 23% | 4000 | 700 | In Progress | 3300 | Within Budget | 584
Mobile App Launch | Analytics Integration | Daniel Park | Low | 2025-01-04 | 2025-01-28 |  | 37% | 40000 | 14600 | In Progress | 25400 | Within Budget | 601
Website Redesign | Status Reporting | Amanda Foster | Medium | 2024-07-10 | 2024-07-29 | 2024-07-26 | 100% | 15000 | 17800 | Completed | -2800 | Over Budget | -3
Budget Planning Tool | Quality Assurance | Hannah White | Medium | 2024-03-27 | 2024-05-01 | 2024-05-06 | 100% | 76000 | 100700 | Completed | -24700 | Over Budget | 5
Product Launch Q1 | Frontend Development | Hannah White | High | 2024-12-19 | 2025-02-03 | 2025-03-18 | 100% | 58000 | 66900 | Completed | -8900 | Over Budget | 43
CRM Migration | Content Creation | Sarah Chen | Medium | 2024-11-28 | 2024-12-11 | 2024-12-15 | 100% | 13000 | 14800 | Completed | -1800 | Over Budget | 4
Training Platform | Communication Plan | Hannah White | Critical | 2024-11-01 | 2024-11-14 |  | 68% | 38000 | 35800 | Delayed | 2200 | Within Budget | 676
Mobile App Launch | Requirements Gathering | Robert Garcia | Low | 2024-05-09 | 2024-05-16 | 2024-05-11 | 20% | 5000 | 1300 | Cancelled | 3700 | Within Budget | -5
Vendor Portal | Content Creation | Kevin O'Brien | Low | 2025-04-01 | 2025-04-13 |  | 59% | 42000 | 22700 | In Progress | 19300 | Within Budget | 526
Vendor Portal | Iteration Planning | Jennifer Lee | Low | 2025-05-11 | 2025-06-04 |  | 0% | 26000 | 0 | Not Started | 26000 | Within Budget | 474
Data Warehouse Build | Stakeholder Interviews | Ahmed Hassan | High | 2024-06-30 | 2024-07-07 | 2024-07-02 | 10% | 8000 | 2700 | Cancelled | 5300 | Within Budget | -5
Product Launch Q1 | Code Review | Natasha Singh | High | 2024-05-09 | 2024-05-31 | 2024-06-04 | 100% | 33000 | 35900 | Completed | -2900 | Over Budget | 4
Onboarding Automation | Market Research | Rachel Thompson | Critical | 2024-09-20 | 2024-09-25 | 2024-09-17 | 100% | 10000 | 8700 | Completed | 1300 | Within Budget | -8
ERP Implementation | Security Review | Brian Taylor | High | 2024-02-28 | 2024-03-07 | 2024-03-11 | 100% | 13000 | 14400 | Completed | -1400 | Over Budget | 4
Product Launch Q1 | System Configuration | Olivia Martinez | Medium | 2025-03-15 | 2025-04-03 |  | 75% | 25000 | 19700 | In Progress | 5300 | Within Budget | 536
Data Warehouse Build | Vendor Evaluation | Sarah Chen | High | 2024-11-29 | 2024-12-18 | 2025-01-02 | 100% | 10000 | 11800 | Completed | -1800 | Over Budget | 15
Website Redesign | Unit Testing | Brian Taylor | Low | 2025-04-28 | 2025-05-30 |  | 35% | 87000 | 35900 | In Progress | 51100 | Within Budget | 479
DevOps Pipeline | User Acceptance Testing | Michael Brown | High | 2024-10-16 | 2024-10-25 | 2024-11-18 | 100% | 7000 | 7900 | Completed | -900 | Over Budget | 24
Analytics Dashboard | Budget Review | Natasha Singh | Low | 2024-11-28 | 2024-12-31 | 2025-02-04 | 100% | 86000 | 93200 | Completed | -7200 | Over Budget | 35
Onboarding Automation | Technical Architecture | Sarah Chen | Low | 2024-03-11 | 2024-03-28 | 2024-05-05 | 100% | 34000 | 40900 | Completed | -6900 | Over Budget | 38
Mobile App Launch | SEO Optimization | Kevin O'Brien | Low | 2025-03-20 | 2025-04-19 |  | 0% | 37000 | 0 | Not Started | 37000 | Within Budget | 520
HR System Upgrade | Stakeholder Interviews | Priya Patel | High | 2024-10-23 | 2024-10-31 |  | 61% | 3000 | 3700 | Delayed | -700 | Over Budget | 690
Inventory System | Training Materials | Elena Rodriguez | Low | 2025-05-19 | 2025-05-30 |  | 47% | 17000 | 6700 | In Progress | 10300 | Within Budget | 479
Training Platform | API Development | David Kim | Medium | 2025-06-13 | 2025-06-22 |  | 0% | 11000 | 0 | Not Started | 11000 | Within Budget | 456
Annual Report | Iteration Planning | Carlos Mendez | High | 2024-12-30 | 2025-02-02 |  | 80% | 40000 | 37400 | Delayed | 2600 | Within Budget | 596
Social Media Revamp | Integration Testing | Natasha Singh | High | 2024-11-30 | 2024-12-31 | 2024-12-31 | 100% | 91000 | 109600 | Completed | -18600 | Over Budget | 0
CRM Migration | Asset Design | Olivia Martinez | Low | 2025-04-08 | 2025-05-07 |  | 36% | 35000 | 12600 | In Progress | 22400 | Within Budget | 502
Training Platform | Accessibility Audit | Michael Brown | Low | 2024-05-23 | 2024-06-18 | 2024-06-19 | 100% | 41000 | 54700 | Completed | -13700 | Over Budget | 1
Website Redesign | Contract Negotiation | Tom Mitchell | Medium | 2024-12-12 | 2024-12-19 | 2024-12-29 | 100% | 3000 | 3900 | Completed | -900 | Over Budget | 10
Brand Refresh | Go-Live Preparation | Daniel Park | High | 2024-02-07 | 2024-02-21 | 2024-03-08 | 100% | 15000 | 15400 | Completed | -400 | Over Budget | 16
Website Redesign | Backup Configuration | Daniel Park | Critical | 2024-06-20 | 2024-07-16 |  | 29% | 22000 | 28300 | Delayed | -6300 | Over Budget | 797
Marketing Automation | Infrastructure Setup | Ahmed Hassan | Low | 2024-10-22 | 2024-11-18 | 2024-11-10 | 100% | 39000 | 43000 | Completed | -4000 | Over Budget | -8
Office Relocation | Competitive Analysis | James Wilson | Medium | 2024-04-02 | 2024-04-14 | 2024-05-01 | 100% | 39000 | 38800 | Completed | 200 | Within Budget | 17
API Gateway | Competitive Analysis | Elena Rodriguez | Low | 2024-10-10 | 2024-11-11 | 2024-11-09 | 100% | 49000 | 60500 | Completed | -11500 | Over Budget | -2
Annual Report | Prototype Development | Emily Davis | High | 2024-03-11 | 2024-03-28 | 2024-04-25 | 100% | 18000 | 17300 | Completed | 700 | Within Budget | 28
Chatbot Development | Training Materials | Brian Taylor | High | 2025-03-22 | 2025-03-30 |  | 0% | 3000 | 0 | Not Started | 3000 | Within Budget | 540
CRM Migration | Code Review | James Wilson | Medium | 2024-09-04 | 2024-09-16 | 2024-09-14 | 100% | 41000 | 47000 | Completed | -6000 | Over Budget | -2
Vendor Portal | Optimization | Emily Davis | High | 2024-08-19 | 2024-09-07 | 2024-08-22 | 10% | 31000 | 6100 | Cancelled | 24900 | Within Budget | -16
HR System Upgrade | Stakeholder Interviews | David Kim | Medium | 2025-06-23 | 2025-06-28 |  | 15% | 8000 | 1100 | In Progress | 6900 | Within Budget | 450
Payment Integration | Bug Fixes | Hannah White | Medium | 2025-03-05 | 2025-03-15 |  | 0% | 3000 | 0 | Not Started | 3000 | Within Budget | 555
Vendor Portal | Prototype Development | David Kim | Medium | 2025-03-25 | 2025-04-18 |  | 0% | 42000 | 0 | Not Started | 42000 | Within Budget | 521
Payment Integration | Wireframing | Sarah Chen | Low | 2024-07-05 | 2024-07-31 | 2024-08-09 | 100% | 31000 | 40300 | Completed | -9300 | Over Budget | 9
Website Redesign | Competitive Analysis | Chris Evans | Medium | 2025-01-15 | 2025-01-23 |  | 55% | 8000 | 3500 | On Hold | 4500 | Within Budget | 606
Website Redesign | Deployment Planning | Ahmed Hassan | Low | 2025-02-12 | 2025-02-28 |  | 17% | 31000 | 5400 | In Progress | 25600 | Within Budget | 570
Performance Review System | User Acceptance Testing | Amanda Foster | Low | 2025-01-02 | 2025-01-28 |  | 64% | 15000 | 11400 | In Progress | 3600 | Within Budget | 601
API Gateway | Prototype Development | James Wilson | High | 2025-01-21 | 2025-02-23 |  | 26% | 81000 | 27700 | On Hold | 53300 | Within Budget | 575
DevOps Pipeline | Code Review | Daniel Park | High | 2025-04-06 | 2025-04-22 |  | 0% | 38000 | 0 | Not Started | 38000 | Within Budget | 517
Cloud Infrastructure | Communication Plan | Robert Garcia | Critical | 2024-03-03 | 2024-03-16 |  | 61% | 41000 | 52000 | Delayed | -11000 | Over Budget | 919
HR System Upgrade | Analytics Integration | Ahmed Hassan | High | 2024-01-07 | 2024-02-09 | 2024-02-11 | 100% | 40000 | 39100 | Completed | 900 | Within Budget | 2
Marketing Automation | API Development | Emily Davis | Medium | 2024-05-27 | 2024-06-07 | 2024-05-30 | 0% | 11000 | 4100 | Cancelled | 6900 | Within Budget | -8
Budget Planning Tool | Frontend Development | Rachel Thompson | Medium | 2025-06-02 | 2025-08-14 |  | 0% | 177000 | 0 | Not Started | 177000 | Within Budget | 403
Product Launch Q1 | UI/UX Design | Robert Garcia | Critical | 2024-11-22 | 2024-12-06 | 2025-01-18 | 100% | 42000 | 48400 | Completed | -6400 | Over Budget | 43
Office Relocation | Code Review | Elena Rodriguez | Medium | 2024-01-05 | 2024-01-31 | 2024-02-01 | 100% | 21000 | 22600 | Completed | -1600 | Over Budget | 1
API Gateway | Documentation | Michael Brown | Medium | 2025-04-17 | 2025-05-02 |  | 40% | 37000 | 14500 | In Progress | 22500 | Within Budget | 507
Inventory System | Sprint Planning | Priya Patel | Low | 2024-03-27 | 2024-04-01 | 2024-04-05 | 100% | 7000 | 6800 | Completed | 200 | Within Budget | 4
Budget Planning Tool | Change Management | David Kim | Critical | 2024-12-16 | 2025-01-12 |  | 44% | 14000 | 7000 | In Progress | 7000 | Within Budget | 617
Email Platform Migration | Stakeholder Interviews | Marcus Johnson | High | 2024-03-23 | 2024-03-28 |  | 36% | 15000 | 12700 | Delayed | 2300 | Within Budget | 907
Compliance Overhaul | Deployment Planning | Brian Taylor | High | 2024-10-28 | 2024-12-01 | 2024-12-05 | 100% | 92000 | 102400 | Completed | -10400 | Over Budget | 4
Product Launch Q1 | Backend Development | Olivia Martinez | Critical | 2024-09-01 | 2024-10-16 | 2024-10-30 | 100% | 31000 | 35500 | Completed | -4500 | Over Budget | 14
Analytics Dashboard | Content Creation | Priya Patel | Low | 2024-08-14 | 2024-09-02 | 2024-09-05 | 100% | 49000 | 58400 | Completed | -9400 | Over Budget | 3
Onboarding Automation | SEO Optimization | Jennifer Lee | Low | 2024-08-02 | 2024-08-22 | 2024-08-10 | 20% | 22000 | 4300 | Cancelled | 17700 | Within Budget | -12
Compliance Overhaul | Risk Assessment | Emily Davis | Critical | 2024-07-29 | 2024-08-25 | 2024-08-29 | 100% | 18000 | 15300 | Completed | 2700 | Within Budget | 4
Payment Integration | Analytics Integration | Emily Davis | High | 2024-12-01 | 2024-12-28 | 2025-01-03 | 100% | 47000 | 50700 | Completed | -3700 | Over Budget | 6
API Gateway | Bug Fixes | Michael Brown | Low | 2025-03-25 | 2025-04-10 |  | 0% | 33000 | 0 | Not Started | 33000 | Within Budget | 529
Payment Integration | Asset Design | Lisa Wang | High | 2025-01-04 | 2025-01-12 |  | 12% | 15000 | 2100 | In Progress | 12900 | Within Budget | 617
Chatbot Development | Content Creation | Priya Patel | Low | 2024-01-26 | 2024-02-18 | 2024-01-30 | 25% | 27000 | 5700 | Cancelled | 21300 | Within Budget | -19
Budget Planning Tool | Optimization | Lisa Wang | High | 2024-07-27 | 2024-08-03 | 2024-09-05 | 100% | 4000 | 4900 | Completed | -900 | Over Budget | 33
Inventory System | Feedback Collection | Priya Patel | Medium | 2024-07-06 | 2024-07-14 | 2024-07-09 | 20% | 8000 | 1600 | Cancelled | 6400 | Within Budget | -5
Marketing Automation | Training Materials | Stephanie Adams | Low | 2024-02-02 | 2024-02-21 | 2024-02-06 | 15% | 33000 | 10900 | Cancelled | 22100 | Within Budget | -15
ERP Implementation | Risk Assessment | Carlos Mendez | High | 2024-01-21 | 2024-02-21 | 2024-02-14 | 100% | 78000 | 76600 | Completed | 1400 | Within Budget | -7
Email Platform Migration | Contract Negotiation | James Wilson | Low | 2024-02-09 | 2024-02-25 | 2024-02-27 | 100% | 44000 | 52600 | Completed | -8600 | Over Budget | 2
Office Relocation | Data Migration | Robert Garcia | High | 2024-05-05 | 2024-07-22 |  | 61% | 68000 | 40000 | Delayed | 28000 | Within Budget | 791
Product Launch Q1 | UI/UX Design | Chris Evans | Critical | 2024-09-19 | 2024-10-19 | 2024-10-27 | 100% | 33000 | 29900 | Completed | 3100 | Within Budget | 8
Budget Planning Tool | User Acceptance Testing | Marcus Johnson | Medium | 2025-05-27 | 2025-07-01 |  | 68% | 71000 | 49400 | In Progress | 21600 | Within Budget | 447
Analytics Dashboard | Analytics Integration | Elena Rodriguez | High | 2024-05-18 | 2024-05-27 | 2024-07-05 | 100% | 15000 | 19900 | Completed | -4900 | Over Budget | 39
Annual Report | Budget Review | Hannah White | Low | 2024-03-19 | 2024-04-03 | 2024-04-07 | 100% | 35000 | 44400 | Completed | -9400 | Over Budget | 4
Budget Planning Tool | Backup Configuration | Rachel Thompson | High | 2024-09-05 | 2024-09-21 | 2024-10-01 | 100% | 40000 | 46100 | Completed | -6100 | Over Budget | 10
Product Launch Q2 | Vendor Evaluation | Robert Garcia | Medium | 2024-10-10 | 2024-11-10 | 2024-10-15 | 15% | 97000 | 37800 | Cancelled | 59200 | Within Budget | -26
Inventory System | System Configuration | Marcus Johnson | High | 2025-06-11 | 2025-06-26 |  | 0% | 35000 | 0 | Not Started | 35000 | Within Budget | 452
ERP Implementation | Accessibility Audit | Priya Patel | High | 2025-02-23 | 2025-03-30 |  | 51% | 64000 | 35800 | In Progress | 28200 | Within Budget | 540
Website Redesign | Sprint Planning | Hannah White | High | 2025-01-01 | 2025-01-13 |  | 35% | 43000 | 4800 | On Hold | 38200 | Within Budget | 616
CRM Migration | User Acceptance Testing | Carlos Mendez | High | 2025-06-23 | 2025-07-02 |  | 0% | 11000 | 0 | Not Started | 11000 | Within Budget | 446
Analytics Dashboard | Technical Architecture | Sarah Chen | Critical | 2024-10-25 | 2024-11-17 | 2024-11-22 | 100% | 28000 | 26900 | Completed | 1100 | Within Budget | 5
Brand Refresh | Optimization | Jessica Turner | Medium | 2024-07-25 | 2024-08-05 | 2024-08-05 | 100% | 39000 | 39900 | Completed | -900 | Over Budget | 0
CRM Migration | SEO Optimization | Priya Patel | Medium | 2024-11-18 | 2024-12-23 | 2024-11-29 | 15% | 88000 | 20800 | Cancelled | 67200 | Within Budget | -24
Analytics Dashboard | Analytics Integration | Hannah White | Critical | 2025-01-31 | 2025-03-01 |  | 61% | 34000 | 40200 | Delayed | -6200 | Over Budget | 569
DevOps Pipeline | Requirements Gathering | Robert Garcia | High | 2024-12-26 | 2025-01-07 | 2025-02-04 | 100% | 12000 | 12800 | Completed | -800 | Over Budget | 28
Customer Portal | Database Design | Jessica Turner | Medium | 2024-05-20 | 2024-06-09 | 2024-06-23 | 100% | 33000 | 31500 | Completed | 1500 | Within Budget | 14
Budget Planning Tool | Technical Architecture | Olivia Martinez | Critical | 2024-10-19 | 2024-11-21 | 2024-11-21 | 100% | 63000 | 69300 | Completed | -6300 | Over Budget | 0
Marketing Automation | Budget Review | David Kim | Low | 2024-07-09 | 2024-07-18 | 2024-07-12 | 20% | 7000 | 600 | Cancelled | 6400 | Within Budget | -6
Budget Planning Tool | Technical Architecture | James Wilson | Medium | 2025-02-25 | 2025-03-22 |  | 42% | 40000 | 10600 | On Hold | 29400 | Within Budget | 548
Social Media Revamp | User Training | Rachel Thompson | High | 2024-04-14 | 2024-04-27 | 2024-05-19 | 100% | 15000 | 20900 | Completed | -5900 | Over Budget | 22
Chatbot Development | Quality Assurance | Kevin O'Brien | High | 2024-04-03 | 2024-04-20 | 2024-04-28 | 100% | 21000 | 19200 | Completed | 1800 | Within Budget | 8
Inventory System | Analytics Integration | Jessica Turner | Low | 2024-04-23 | 2024-05-23 | 2024-06-13 | 100% | 17000 | 19800 | Completed | -2800 | Over Budget | 21
Office Relocation | Vendor Evaluation | Tom Mitchell | Critical | 2024-07-11 | 2024-07-24 | 2024-08-12 | 100% | 37000 | 50500 | Completed | -13500 | Over Budget | 19
Analytics Dashboard | Requirements Gathering | Priya Patel | Medium | 2024-01-14 | 2024-01-27 | 2024-02-09 | 100% | 26000 | 28200 | Completed | -2200 | Over Budget | 13
Training Platform | Stakeholder Interviews | Michael Brown | High | 2024-10-17 | 2024-10-23 | 2024-11-09 | 100% | 8000 | 9300 | Completed | -1300 | Over Budget | 17
Vendor Portal | Risk Assessment | Tom Mitchell | Low | 2025-04-06 | 2025-05-01 |  | 0% | 41000 | 0 | Not Started | 41000 | Within Budget | 508
Email Platform Migration | Sprint Planning | Stephanie Adams | Low | 2025-01-16 | 2025-01-30 |  | 76% | 46000 | 41100 | In Progress | 4900 | Within Budget | 599
Inventory System | Code Review | Brian Taylor | Medium | 2025-05-23 | 2025-06-26 |  | 0% | 87000 | 0 | Not Started | 87000 | Within Budget | 452
Inventory System | Compliance Check | Ahmed Hassan | Critical | 2024-01-28 | 2024-02-15 | 2024-01-30 | 10% | 40000 | 3000 | Cancelled | 37000 | Within Budget | -16
Social Media Revamp | Performance Testing | Daniel Park | High | 2025-02-02 | 2025-02-20 |  | 28% | 46000 | 39800 | Delayed | 6200 | Within Budget | 578
DevOps Pipeline | Backup Configuration | Lisa Wang | Low | 2025-06-22 | 2025-07-27 |  | 0% | 96000 | 0 | Not Started | 96000 | Within Budget | 421
Chatbot Development | Optimization | Jennifer Lee | Low | 2024-08-24 | 2024-09-14 | 2024-09-14 | 100% | 40000 | 52400 | Completed | -12400 | Over Budget | 0
Office Relocation | Go-Live Preparation | Hannah White | High | 2025-06-20 | 2025-07-25 |  | 0% | 67000 | 0 | Not Started | 67000 | Within Budget | 423
Training Platform | Infrastructure Setup | Kevin O'Brien | Medium | 2024-10-18 | 2024-10-29 |  | 57% | 17000 | 11300 | Delayed | 5700 | Within Budget | 692
Onboarding Automation | Post-Launch Review | Robert Garcia | Medium | 2024-07-06 | 2024-08-06 | 2024-09-03 | 100% | 47000 | 54700 | Completed | -7700 | Over Budget | 28
Customer Portal | Post-Launch Review | Amanda Foster | Low | 2024-05-04 | 2024-05-22 | 2024-07-05 | 100% | 22000 | 20800 | Completed | 1200 | Within Budget | 44
Website Redesign | Retrospective | Elena Rodriguez | High | 2024-01-28 | 2024-02-05 | 2024-02-05 | 100% | 7000 | 8700 | Completed | -1700 | Over Budget | 0
Office Relocation | Performance Testing | Olivia Martinez | High | 2024-06-30 | 2024-07-11 |  | 85% | 47000 | 50200 | Delayed | -3200 | Over Budget | 802
Office Relocation | Go-Live Preparation | Kevin O'Brien | High | 2024-06-06 | 2024-07-10 | 2024-06-22 | 20% | 78000 | 30500 | Cancelled | 47500 | Within Budget | -18
Onboarding Automation | Sprint Planning | Natasha Singh | High | 2025-01-01 | 2025-01-10 |  | 70% | 12000 | 9800 | Delayed | 2200 | Within Budget | 619
Payment Integration | Security Review | Rachel Thompson | High | 2024-02-07 | 2024-03-03 | 2024-03-06 | 100% | 35000 | 38500 | Completed | -3500 | Over Budget | 3
API Gateway | User Acceptance Testing | Tom Mitchell | Medium | 2025-03-01 | 2025-03-26 |  | 33% | 39000 | 10800 | On Hold | 28200 | Within Budget | 544
DevOps Pipeline | Backup Configuration | Rachel Thompson | Medium | 2024-08-10 | 2024-08-22 | 2024-09-02 | 100% | 31000 | 37300 | Completed | -6300 | Over Budget | 11
Website Redesign | Bug Fixes | Kevin O'Brien | Medium | 2024-02-24 | 2024-03-22 | 2024-03-23 | 100% | 13000 | 13100 | Completed | -100 | Over Budget | 1
Cloud Infrastructure | Documentation | Olivia Martinez | High | 2024-08-02 | 2024-08-23 | 2024-08-08 | 15% | 27000 | 3700 | Cancelled | 23300 | Within Budget | -15
Budget Planning Tool | Deployment Planning | Kevin O'Brien | Critical | 2024-10-12 | 2024-11-10 | 2024-11-24 | 100% | 44000 | 41800 | Completed | 2200 | Within Budget | 14
Data Warehouse Build | API Development | Ahmed Hassan | Critical | 2024-05-25 | 2024-06-09 | 2024-06-01 | 100% | 41000 | 35600 | Completed | 5400 | Within Budget | -8
API Gateway | Analytics Integration | Sarah Chen | Low | 2025-04-23 | 2025-05-22 |  | 0% | 13000 | 0 | Not Started | 13000 | Within Budget | 487
Marketing Automation | Post-Launch Review | Tom Mitchell | Medium | 2025-01-17 | 2025-01-28 |  | 40% | 33000 | 33100 | Delayed | -100 | Over Budget | 601
Product Launch Q1 | Optimization | Hannah White | High | 2025-01-04 | 2025-01-27 |  | 85% | 15000 | 11700 | In Progress | 3300 | Within Budget | 602
Data Warehouse Build | Budget Review | Sarah Chen | Low | 2025-03-29 | 2025-04-08 |  | 34% | 8000 | 3300 | In Progress | 4700 | Within Budget | 531
Brand Refresh | Iteration Planning | James Wilson | Low | 2025-03-15 | 2025-04-18 |  | 17% | 96000 | 15400 | In Progress | 80600 | Within Budget | 521
Brand Refresh | Status Reporting | Kevin O'Brien | Medium | 2024-10-23 | 2024-11-16 | 2024-11-10 | 100% | 33000 | 39700 | Completed | -6700 | Over Budget | -6
Cloud Infrastructure | Infrastructure Setup | Lisa Wang | Low | 2025-03-22 | 2025-03-30 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 540
CRM Migration | Stakeholder Interviews | Priya Patel | Medium | 2025-05-13 | 2025-05-21 |  | 0% | 9000 | 0 | Not Started | 9000 | Within Budget | 488
Brand Refresh | Deployment Planning | Jennifer Lee | High | 2024-12-05 | 2025-01-06 | 2025-02-10 | 100% | 30000 | 36900 | Completed | -6900 | Over Budget | 35
Email Platform Migration | Performance Testing | Kevin O'Brien | High | 2025-02-25 | 2025-03-12 |  | 25% | 13000 | 1500 | On Hold | 11500 | Within Budget | 558
Budget Planning Tool | API Development | Tom Mitchell | Low | 2024-07-07 | 2024-08-11 | 2024-07-11 | 15% | 40000 | 5100 | Cancelled | 34900 | Within Budget | -31
API Gateway | Documentation | Daniel Park | Critical | 2024-03-07 | 2024-03-14 | 2024-03-11 | 100% | 6000 | 6100 | Completed | -100 | Over Budget | -3
Inventory System | Communication Plan | Jennifer Lee | Critical | 2025-01-07 | 2025-01-23 |  | 41% | 25000 | 8300 | On Hold | 16700 | Within Budget | 606
Mobile App Launch | Database Design | Robert Garcia | Critical | 2024-02-18 | 2024-03-09 | 2024-03-27 | 100% | 36000 | 49600 | Completed | -13600 | Over Budget | 18
Annual Report | Database Design | Ahmed Hassan | High | 2025-02-13 | 2025-03-24 |  | 37% | 35000 | 8500 | On Hold | 26500 | Within Budget | 546
Vendor Portal | User Training | Marcus Johnson | High | 2024-07-27 | 2024-08-20 |  | 67% | 17000 | 12000 | Delayed | 5000 | Within Budget | 762
DevOps Pipeline | Iteration Planning | Marcus Johnson | Medium | 2024-03-02 | 2024-03-31 | 2024-04-18 | 100% | 48000 | 49100 | Completed | -1100 | Over Budget | 18
DevOps Pipeline | Analytics Integration | Natasha Singh | High | 2024-09-25 | 2024-10-09 | 2024-09-29 | 100% | 19000 | 23200 | Completed | -4200 | Over Budget | -10
HR System Upgrade | Unit Testing | Michael Brown | Low | 2024-02-03 | 2024-02-22 |  | 69% | 34000 | 21300 | Delayed | 12700 | Within Budget | 942
Email Platform Migration | Go-Live Preparation | Carlos Mendez | Low | 2024-05-30 | 2024-06-27 | 2024-06-30 | 100% | 31000 | 35400 | Completed | -4400 | Over Budget | 3
Performance Review System | Communication Plan | Priya Patel | High | 2024-07-31 | 2024-08-26 | 2024-08-30 | 100% | 39000 | 36600 | Completed | 2400 | Within Budget | 4
Product Launch Q1 | Sprint Planning | Kevin O'Brien | Low | 2024-07-27 | 2024-08-03 | 2024-08-05 | 100% | 12000 | 15200 | Completed | -3200 | Over Budget | 2
Office Relocation | Market Research | Carlos Mendez | High | 2025-02-13 | 2025-02-25 | 2025-03-13 | 100% | 44000 | 43300 | Completed | 700 | Within Budget | 16
Onboarding Automation | Quality Assurance | Kevin O'Brien | Medium | 2024-11-29 | 2024-12-14 | 2024-12-08 | 100% | 35000 | 32300 | Completed | 2700 | Within Budget | -6
Vendor Portal | Optimization | Olivia Martinez | Medium | 2025-03-27 | 2025-04-19 |  | 0% | 39000 | 0 | Not Started | 39000 | Within Budget | 520
Data Warehouse Build | Risk Assessment | James Wilson | Medium | 2024-01-05 | 2024-01-17 | 2024-02-03 | 100% | 15000 | 19300 | Completed | -4300 | Over Budget | 17
Payment Integration | Post-Launch Review | Ahmed Hassan | High | 2024-01-09 | 2024-01-26 | 2024-02-25 | 100% | 15000 | 16700 | Completed | -1700 | Over Budget | 30
Security Audit | Change Management | Kevin O'Brien | Low | 2024-02-11 | 2024-03-14 | 2024-02-26 | 15% | 36000 | 8000 | Cancelled | 28000 | Within Budget | -17
Budget Planning Tool | User Acceptance Testing | Priya Patel | Low | 2024-03-08 | 2024-04-06 | 2024-04-09 | 100% | 50000 | 58500 | Completed | -8500 | Over Budget | 3
Social Media Revamp | Status Reporting | Lisa Wang | Medium | 2024-12-26 | 2025-01-17 |  | 74% | 46000 | 37300 | Delayed | 8700 | Within Budget | 612
ERP Implementation | Vendor Evaluation | Daniel Park | Medium | 2024-02-26 | 2024-03-18 | 2024-04-28 | 100% | 40000 | 49400 | Completed | -9400 | Over Budget | 41
Data Warehouse Build | Accessibility Audit | Jennifer Lee | Medium | 2024-02-04 | 2024-02-17 | 2024-02-18 | 100% | 49000 | 54500 | Completed | -5500 | Over Budget | 1
Compliance Overhaul | Database Design | Kevin O'Brien | Medium | 2024-06-03 | 2024-07-06 | 2024-07-21 | 100% | 79000 | 77000 | Completed | 2000 | Within Budget | 15
ERP Implementation | Technical Architecture | Elena Rodriguez | Low | 2024-01-05 | 2024-01-27 | 2024-01-14 | 30% | 27000 | 3400 | Cancelled | 23600 | Within Budget | -13
Website Redesign | Competitive Analysis | Carlos Mendez | Low | 2024-01-28 | 2024-02-11 | 2024-02-23 | 100% | 42000 | 47800 | Completed | -5800 | Over Budget | 12
Website Redesign | UI/UX Design | Sarah Chen | Critical | 2024-06-04 | 2024-06-21 | 2024-06-21 | 100% | 27000 | 36700 | Completed | -9700 | Over Budget | 0
Supply Chain Optimization | A/B Testing Setup | Sarah Chen | Medium | 2024-12-02 | 2024-12-24 |  | 69% | 27000 | 34600 | Delayed | -7600 | Over Budget | 636
Payment Integration | Security Review | Robert Garcia | High | 2024-08-20 | 2024-09-19 |  | 79% | 10000 | 12100 | Delayed | -2100 | Over Budget | 732
Performance Review System | Code Review | Stephanie Adams | Medium | 2025-05-07 | 2025-06-10 |  | 40% | 90000 | 36700 | In Progress | 53300 | Within Budget | 468
Supply Chain Optimization | Status Reporting | Carlos Mendez | Low | 2024-04-26 | 2024-05-05 |  | 42% | 8000 | 4300 | Delayed | 3700 | Within Budget | 869
Training Platform | Integration Testing | Sarah Chen | Medium | 2024-03-17 | 2024-04-12 | 2024-04-14 | 100% | 34000 | 39700 | Completed | -5700 | Over Budget | 2
Marketing Automation | Database Design | Kevin O'Brien | High | 2024-04-21 | 2024-05-08 | 2024-06-16 | 100% | 39000 | 42000 | Completed | -3000 | Over Budget | 39
Office Relocation | Asset Design | Rachel Thompson | Medium | 2024-11-15 | 2024-12-07 | 2024-12-19 | 100% | 44000 | 54200 | Completed | -10200 | Over Budget | 12
Cloud Infrastructure | Requirements Gathering | Sarah Chen | Medium | 2025-01-06 | 2025-01-18 | 2025-02-04 | 100% | 26000 | 33700 | Completed | -7700 | Over Budget | 17
Product Launch Q1 | Budget Review | Chris Evans | Medium | 2025-04-24 | 2025-05-04 |  | 29% | 6000 | 1900 | In Progress | 4100 | Within Budget | 505
Data Warehouse Build | Competitive Analysis | Rachel Thompson | High | 2024-01-13 | 2024-01-21 | 2024-01-16 | 0% | 13000 | 3000 | Cancelled | 10000 | Within Budget | -5
Email Platform Migration | Database Design | Lisa Wang | Medium | 2024-07-30 | 2024-08-23 | 2024-08-26 | 100% | 49000 | 56800 | Completed | -7800 | Over Budget | 3
Social Media Revamp | UI/UX Design | Emily Davis | Medium | 2024-08-10 | 2024-09-13 |  | 85% | 44000 | 52900 | Delayed | -8900 | Over Budget | 738
Compliance Overhaul | Feedback Collection | Priya Patel | Medium | 2025-06-08 | 2025-07-01 |  | 67% | 43000 | 30900 | In Progress | 12100 | Within Budget | 447
Onboarding Automation | Bug Fixes | Carlos Mendez | Medium | 2025-02-17 | 2025-02-27 | 2025-03-02 | 100% | 8000 | 7200 | Completed | 800 | Within Budget | 3
Supply Chain Optimization | Stakeholder Interviews | Emily Davis | Low | 2024-12-09 | 2024-12-21 | 2025-02-03 | 100% | 27000 | 24200 | Completed | 2800 | Within Budget | 44
CRM Migration | Security Review | Tom Mitchell | High | 2025-05-09 | 2025-05-23 |  | 0% | 47000 | 0 | Not Started | 47000 | Within Budget | 486
Cloud Infrastructure | UI/UX Design | Ahmed Hassan | Medium | 2025-04-29 | 2025-05-25 |  | 0% | 39000 | 0 | Not Started | 39000 | Within Budget | 484
Website Redesign | Contract Negotiation | Lisa Wang | Low | 2024-05-11 | 2024-06-01 | 2024-06-19 | 100% | 46000 | 44900 | Completed | 1100 | Within Budget | 18
Onboarding Automation | User Acceptance Testing | Priya Patel | Medium | 2024-11-27 | 2024-12-06 |  | 79% | 4000 | 2100 | Delayed | 1900 | Within Budget | 654
Vendor Portal | Go-Live Preparation | Hannah White | High | 2024-12-28 | 2025-01-28 |  | 54% | 97000 | 91300 | Delayed | 5700 | Within Budget | 601
Inventory System | Post-Launch Review | Marcus Johnson | Medium | 2024-08-28 | 2024-09-12 | 2024-08-31 | 0% | 50000 | 17600 | Cancelled | 32400 | Within Budget | -12
Marketing Automation | User Training | Hannah White | Low | 2024-01-28 | 2024-02-15 | 2024-02-20 | 100% | 15000 | 13100 | Completed | 1900 | Within Budget | 5
Vendor Portal | Post-Launch Review | Priya Patel | High | 2025-02-01 | 2025-03-05 |  | 56% | 45000 | 28900 | In Progress | 16100 | Within Budget | 565
Website Redesign | Deployment Planning | Sarah Chen | Critical | 2025-01-05 | 2025-02-09 | 2025-02-26 | 100% | 93000 | 122700 | Completed | -29700 | Over Budget | 17
Payment Integration | Go-Live Preparation | Jessica Turner | High | 2024-07-16 | 2024-07-27 | 2024-07-30 | 100% | 14000 | 17600 | Completed | -3600 | Over Budget | 3
Onboarding Automation | Retrospective | Stephanie Adams | High | 2024-12-28 | 2025-01-03 |  | 59% | 8000 | 7900 | Delayed | 100 | Within Budget | 626
Training Platform | Database Design | Michael Brown | Medium | 2024-07-17 | 2024-08-04 | 2024-08-10 | 100% | 49000 | 64100 | Completed | -15100 | Over Budget | 6
Security Audit | Contract Negotiation | Amanda Foster | Medium | 2024-12-23 | 2025-01-11 |  | 28% | 13000 | 10900 | Delayed | 2100 | Within Budget | 618
Mobile App Launch | Risk Assessment | Michael Brown | High | 2024-01-10 | 2024-02-10 | 2024-03-18 | 100% | 48000 | 51100 | Completed | -3100 | Over Budget | 37
Annual Report | System Configuration | Marcus Johnson | Medium | 2025-01-11 | 2025-02-09 |  | 25% | 20000 | 25600 | Delayed | -5600 | Over Budget | 589
Budget Planning Tool | Prototype Development | Rachel Thompson | High | 2024-03-03 | 2024-04-11 | 2024-05-21 | 100% | 47000 | 50700 | Completed | -3700 | Over Budget | 40
Cloud Infrastructure | Stakeholder Interviews | Hannah White | High | 2024-08-18 | 2024-08-28 | 2024-08-20 | 20% | 10000 | 2200 | Cancelled | 7800 | Within Budget | -8
Email Platform Migration | Market Research | Marcus Johnson | Medium | 2025-02-17 | 2025-02-24 | 2025-03-17 | 100% | 8000 | 6900 | Completed | 1100 | Within Budget | 21
Analytics Dashboard | Performance Testing | Carlos Mendez | Low | 2025-05-22 | 2025-06-07 |  | 34% | 34000 | 12200 | In Progress | 21800 | Within Budget | 471
Website Redesign | Prototype Development | Brian Taylor | Low | 2024-03-26 | 2024-04-28 | 2024-05-01 | 100% | 49000 | 59800 | Completed | -10800 | Over Budget | 3
Social Media Revamp | UI/UX Design | Robert Garcia | Medium | 2024-07-11 | 2024-08-16 | 2024-08-16 | 100% | 72000 | 77500 | Completed | -5500 | Over Budget | 0
Product Launch Q1 | Code Review | Robert Garcia | Medium | 2024-01-20 | 2024-02-20 |  | 42% | 31000 | 38800 | Delayed | -7800 | Over Budget | 944
Social Media Revamp | Go-Live Preparation | Robert Garcia | Critical | 2024-08-17 | 2024-09-04 |  | 75% | 44000 | 24900 | Delayed | 19100 | Within Budget | 747
Compliance Overhaul | Database Design | Tom Mitchell | Medium | 2025-02-23 | 2025-03-22 |  | 53% | 10000 | 7200 | Delayed | 2800 | Within Budget | 548
Annual Report | Integration Testing | Lisa Wang | Medium | 2024-12-10 | 2024-12-21 | 2024-12-12 | 100% | 12000 | 12000 | Completed | 0 | Within Budget | -9
Security Audit | Bug Fixes | Jessica Turner | High | 2025-03-16 | 2025-04-18 |  | 0% | 74000 | 0 | Not Started | 74000 | Within Budget | 521
Vendor Portal | Content Creation | Stephanie Adams | Medium | 2024-08-12 | 2024-09-14 | 2024-09-14 | 100% | 84000 | 106600 | Completed | -22600 | Over Budget | 0
Onboarding Automation | Quality Assurance | Stephanie Adams | High | 2024-06-03 | 2024-07-07 |  | 25% | 62000 | 47900 | Delayed | 14100 | Within Budget | 806
Onboarding Automation | Compliance Check | Robert Garcia | Critical | 2024-02-23 | 2024-03-28 | 2024-04-18 | 100% | 85000 | 91600 | Completed | -6600 | Over Budget | 21
Product Launch Q2 | Market Research | Emily Davis | Medium | 2025-02-10 | 2025-02-19 |  | 46% | 2000 | 900 | In Progress | 1100 | Within Budget | 579
Training Platform | Backup Configuration | David Kim | Medium | 2024-07-22 | 2024-08-11 | 2024-08-25 | 100% | 21000 | 24400 | Completed | -3400 | Over Budget | 14
ERP Implementation | Communication Plan | Stephanie Adams | High | 2024-07-31 | 2024-08-25 | 2024-09-02 | 100% | 26000 | 25100 | Completed | 900 | Within Budget | 8
Supply Chain Optimization | Code Review | Lisa Wang | High | 2024-10-23 | 2024-11-02 | 2024-11-26 | 100% | 7000 | 8000 | Completed | -1000 | Over Budget | 24
Analytics Dashboard | Infrastructure Setup | Tom Mitchell | High | 2024-06-24 | 2024-07-04 | 2024-08-10 | 100% | 4000 | 5100 | Completed | -1100 | Over Budget | 37
Marketing Automation | Documentation | Jessica Turner | Medium | 2024-01-30 | 2024-02-26 | 2024-02-02 | 20% | 13000 | 3700 | Cancelled | 9300 | Within Budget | -24
DevOps Pipeline | Risk Assessment | Jessica Turner | Critical | 2025-03-06 | 2025-03-15 |  | 42% | 5000 | 2100 | On Hold | 2900 | Within Budget | 555
Data Warehouse Build | User Acceptance Testing | Marcus Johnson | Medium | 2025-03-19 | 2025-04-04 |  | 0% | 30000 | 0 | Not Started | 30000 | Within Budget | 535
DevOps Pipeline | Asset Design | David Kim | Low | 2024-01-08 | 2024-01-20 | 2024-03-05 | 100% | 32000 | 36800 | Completed | -4800 | Over Budget | 45
Mobile App Launch | Integration Testing | Brian Taylor | High | 2025-05-13 | 2025-06-16 |  | 0% | 71000 | 0 | Not Started | 71000 | Within Budget | 462
Supply Chain Optimization | Bug Fixes | Emily Davis | Low | 2024-03-01 | 2024-03-13 | 2024-03-14 | 100% | 48000 | 59600 | Completed | -11600 | Over Budget | 1
Performance Review System | Change Management | Lisa Wang | High | 2024-05-29 | 2024-06-26 | 2024-06-27 | 100% | 40000 | 44600 | Completed | -4600 | Over Budget | 1
DevOps Pipeline | Compliance Check | Hannah White | Medium | 2025-06-18 | 2025-06-29 |  | 0% | 21000 | 0 | Not Started | 21000 | Within Budget | 449
Brand Refresh | Frontend Development | Natasha Singh | Medium | 2024-01-27 | 2024-03-11 |  | 77% | 79000 | 96800 | Delayed | -17800 | Over Budget | 924
Cloud Infrastructure | Bug Fixes | Priya Patel | Low | 2024-03-13 | 2024-03-21 | 2024-03-20 | 100% | 11000 | 13600 | Completed | -2600 | Over Budget | -1
Email Platform Migration | Compliance Check | Stephanie Adams | Critical | 2024-02-02 | 2024-02-11 |  | 59% | 13000 | 8300 | Delayed | 4700 | Within Budget | 953
Customer Portal | Code Review | Chris Evans | High | 2024-09-27 | 2024-10-13 |  | 23% | 36000 | 21400 | Delayed | 14600 | Within Budget | 708
Vendor Portal | Analytics Integration | Robert Garcia | Medium | 2025-02-02 | 2025-02-11 |  | 14% | 9000 | 5200 | On Hold | 3800 | Within Budget | 587
Product Launch Q2 | Unit Testing | Carlos Mendez | Medium | 2024-11-30 | 2024-12-11 | 2024-12-08 | 100% | 47000 | 49200 | Completed | -2200 | Over Budget | -3
Chatbot Development | Optimization | Hannah White | Low | 2025-03-07 | 2025-03-16 |  | 25% | 14000 | 7900 | On Hold | 6100 | Within Budget | 554
Analytics Dashboard | User Training | Carlos Mendez | Medium | 2024-01-24 | 2024-02-06 | 2024-03-09 | 100% | 40000 | 56000 | Completed | -16000 | Over Budget | 32
Product Launch Q2 | UI/UX Design | Stephanie Adams | High | 2025-05-19 | 2025-06-14 |  | 0% | 44000 | 0 | Not Started | 44000 | Within Budget | 464
Website Redesign | Communication Plan | Robert Garcia | Medium | 2024-09-09 | 2024-09-16 | 2024-09-24 | 100% | 5000 | 5200 | Completed | -200 | Over Budget | 8
Mobile App Launch | Market Research | Natasha Singh | High | 2024-02-17 | 2024-02-26 | 2024-03-01 | 100% | 5000 | 5500 | Completed | -500 | Over Budget | 4
Payment Integration | Stakeholder Interviews | Natasha Singh | Low | 2025-01-13 | 2025-01-21 | 2025-01-19 | 100% | 2000 | 2100 | Completed | -100 | Over Budget | -2
API Gateway | Optimization | Priya Patel | Medium | 2024-01-13 | 2024-02-09 |  | 77% | 26000 | 30000 | Delayed | -4000 | Over Budget | 955
Chatbot Development | Iteration Planning | Olivia Martinez | Critical | 2025-06-25 | 2025-07-03 |  | 0% | 7000 | 0 | Not Started | 7000 | Within Budget | 445
Chatbot Development | Contract Negotiation | Jennifer Lee | Medium | 2025-05-25 | 2025-06-03 |  | 0% | 8000 | 0 | Not Started | 8000 | Within Budget | 475
Cloud Infrastructure | Data Migration | Sarah Chen | Medium | 2024-09-05 | 2024-11-16 | 2024-12-14 | 100% | 172000 | 164300 | Completed | 7700 | Within Budget | 28
Onboarding Automation | Vendor Evaluation | Brian Taylor | Critical | 2024-05-08 | 2024-06-10 | 2024-06-17 | 100% | 37000 | 34800 | Completed | 2200 | Within Budget | 7
HR System Upgrade | Backup Configuration | Kevin O'Brien | Low | 2024-11-28 | 2024-12-22 | 2024-12-27 | 100% | 45000 | 53700 | Completed | -8700 | Over Budget | 5
CRM Migration | Integration Testing | Stephanie Adams | Medium | 2025-04-26 | 2025-05-23 |  | 0% | 19000 | 0 | Not Started | 19000 | Within Budget | 486
Payment Integration | Data Migration | Jennifer Lee | Medium | 2024-12-09 | 2025-02-05 |  | 58% | 60000 | 25200 | On Hold | 34800 | Within Budget | 593
Chatbot Development | Monitoring Setup | Robert Garcia | High | 2024-03-05 | 2024-04-03 | 2024-04-29 | 100% | 10000 | 13700 | Completed | -3700 | Over Budget | 26
Payment Integration | Status Reporting | Sarah Chen | High | 2025-06-03 | 2025-06-24 |  | 35% | 26000 | 9700 | In Progress | 16300 | Within Budget | 454
Product Launch Q2 | Frontend Development | Priya Patel | Low | 2025-02-21 | 2025-04-06 |  | 66% | 97000 | 69300 | In Progress | 27700 | Within Budget | 533
Marketing Automation | Iteration Planning | Sarah Chen | Medium | 2025-01-30 | 2025-03-01 | 2025-03-04 | 100% | 43000 | 40000 | Completed | 3000 | Within Budget | 3
Office Relocation | Budget Review | Rachel Thompson | High | 2024-09-28 | 2024-10-25 | 2024-10-30 | 100% | 44000 | 61400 | Completed | -17400 | Over Budget | 5
Performance Review System | Content Creation | Stephanie Adams | Medium | 2025-01-29 | 2025-02-10 | 2025-02-03 | 100% | 30000 | 33200 | Completed | -3200 | Over Budget | -7
HR System Upgrade | User Training | Chris Evans | Low | 2024-06-04 | 2024-06-13 | 2024-06-14 | 100% | 7000 | 9600 | Completed | -2600 | Over Budget | 1
Training Platform | Competitive Analysis | Daniel Park | Medium | 2024-06-04 | 2024-07-08 |  | 29% | 40000 | 41700 | Delayed | -1700 | Over Budget | 805
Customer Portal | Unit Testing | Olivia Martinez | High | 2025-05-16 | 2025-05-28 |  | 0% | 48000 | 0 | Not Started | 48000 | Within Budget | 481
Brand Refresh | Asset Design | Daniel Park | Medium | 2024-06-26 | 2024-07-16 |  | 80% | 32000 | 25800 | Delayed | 6200 | Within Budget | 797
API Gateway | Backup Configuration | Brian Taylor | Low | 2025-04-09 | 2025-05-13 |  | 37% | 40000 | 17200 | In Progress | 22800 | Within Budget | 496
DevOps Pipeline | Documentation | Daniel Park | Critical | 2024-09-05 | 2024-10-10 |  | 51% | 100000 | 107800 | Delayed | -7800 | Over Budget | 711
Security Audit | A/B Testing Setup | Brian Taylor | High | 2024-01-28 | 2024-02-04 | 2024-01-31 | 30% | 7000 | 400 | Cancelled | 6600 | Within Budget | -4
Office Relocation | Sprint Planning | Olivia Martinez | High | 2024-04-03 | 2024-04-13 | 2024-04-05 | 15% | 10000 | 3500 | Cancelled | 6500 | Within Budget | -8
Data Warehouse Build | Communication Plan | Carlos Mendez | High | 2024-08-22 | 2024-09-20 | 2024-09-12 | 100% | 38000 | 33700 | Completed | 4300 | Within Budget | -8
CRM Migration | Retrospective | Ahmed Hassan | Low | 2025-05-11 | 2025-05-20 |  | 22% | 13000 | 3000 | In Progress | 10000 | Within Budget | 489
Security Audit | Iteration Planning | Emily Davis | Medium | 2024-10-24 | 2024-11-14 | 2024-11-05 | 100% | 29000 | 39100 | Completed | -10100 | Over Budget | -9
HR System Upgrade | Deployment Planning | Carlos Mendez | High | 2024-04-23 | 2024-05-01 | 2024-05-01 | 100% | 5000 | 5400 | Completed | -400 | Over Budget | 0
Compliance Overhaul | Accessibility Audit | Ahmed Hassan | High | 2024-08-03 | 2024-09-07 | 2024-08-29 | 100% | 64000 | 56500 | Completed | 7500 | Within Budget | -9
Office Relocation | API Development | Sarah Chen | Medium | 2024-03-30 | 2024-04-25 | 2024-04-09 | 20% | 10000 | 2900 | Cancelled | 7100 | Within Budget | -16
Brand Refresh | Backend Development | Robert Garcia | Critical | 2025-01-24 | 2025-03-04 | 2025-03-05 | 100% | 44000 | 40100 | Completed | 3900 | Within Budget | 1
Vendor Portal | Market Research | Elena Rodriguez | Medium | 2024-11-18 | 2024-11-23 | 2024-11-25 | 100% | 13000 | 15600 | Completed | -2600 | Over Budget | 2
Cloud Infrastructure | Monitoring Setup | Michael Brown | High | 2024-03-28 | 2024-04-04 | 2024-03-30 | 15% | 13000 | 1400 | Cancelled | 11600 | Within Budget | -5
Annual Report | Bug Fixes | Robert Garcia | Medium | 2024-03-22 | 2024-04-19 |  | 50% | 29000 | 20200 | Delayed | 8800 | Within Budget | 885
DevOps Pipeline | Feedback Collection | Carlos Mendez | Low | 2025-04-30 | 2025-05-18 |  | 0% | 33000 | 0 | Not Started | 33000 | Within Budget | 491
Cloud Infrastructure | Status Reporting | Marcus Johnson | Low | 2024-02-09 | 2024-03-03 | 2024-03-19 | 100% | 39000 | 35200 | Completed | 3800 | Within Budget | 16
CRM Migration | Retrospective | Kevin O'Brien | Critical | 2024-07-01 | 2024-07-09 | 2024-07-04 | 30% | 13000 | 2100 | Cancelled | 10900 | Within Budget | -5
Performance Review System | User Training | Robert Garcia | High | 2025-02-12 | 2025-02-27 |  | 29% | 42000 | 5600 | On Hold | 36400 | Within Budget | 571
Vendor Portal | Content Creation | Jennifer Lee | Medium | 2024-02-13 | 2024-02-26 | 2024-02-14 | 25% | 49000 | 3600 | Cancelled | 45400 | Within Budget | -12
HR System Upgrade | Iteration Planning | Ahmed Hassan | Medium | 2025-02-23 | 2025-03-14 |  | 47% | 43000 | 4400 | On Hold | 38600 | Within Budget | 556
Vendor Portal | Unit Testing | Rachel Thompson | High | 2024-02-14 | 2024-03-02 |  | 73% | 30000 | 31700 | Delayed | -1700 | Over Budget | 933
Mobile App Launch | Change Management | Emily Davis | Low | 2024-04-05 | 2024-04-22 | 2024-04-08 | 20% | 42000 | 6200 | Cancelled | 35800 | Within Budget | -14
Brand Refresh | Content Creation | Jessica Turner | High | 2024-01-31 | 2024-02-16 | 2024-03-24 | 100% | 18000 | 24900 | Completed | -6900 | Over Budget | 37
Security Audit | Optimization | Amanda Foster | Low | 2024-02-21 | 2024-03-07 |  | 77% | 38000 | 34500 | Delayed | 3500 | Within Budget | 928
CRM Migration | Content Creation | Kevin O'Brien | Critical | 2024-01-31 | 2024-02-26 | 2024-03-01 | 100% | 34000 | 44700 | Completed | -10700 | Over Budget | 4
Cloud Infrastructure | Market Research | Emily Davis | Low | 2024-06-28 | 2024-07-10 | 2024-07-13 | 100% | 24000 | 31400 | Completed | -7400 | Over Budget | 3
Cloud Infrastructure | Asset Design | Stephanie Adams | Medium | 2024-07-27 | 2024-08-10 | 2024-08-10 | 100% | 42000 | 38400 | Completed | 3600 | Within Budget | 0
Customer Portal | Change Management | Daniel Park | High | 2024-12-06 | 2024-12-23 | 2024-12-26 | 100% | 31000 | 29800 | Completed | 1200 | Within Budget | 3
Onboarding Automation | Risk Assessment | Jennifer Lee | Medium | 2024-05-03 | 2024-05-11 |  | 27% | 12000 | 8600 | Delayed | 3400 | Within Budget | 863
Product Launch Q1 | Backup Configuration | Jessica Turner | Medium | 2025-01-31 | 2025-02-20 | 2025-02-23 | 100% | 22000 | 30800 | Completed | -8800 | Over Budget | 3
Email Platform Migration | Sprint Planning | Natasha Singh | Low | 2025-01-08 | 2025-01-19 | 2025-01-12 | 100% | 33000 | 38400 | Completed | -5400 | Over Budget | -7
CRM Migration | Quality Assurance | Brian Taylor | Critical | 2024-10-17 | 2024-10-27 | 2024-10-17 | 100% | 3000 | 2600 | Completed | 400 | Within Budget | -10
Mobile App Launch | Monitoring Setup | Stephanie Adams | High | 2024-09-16 | 2024-10-17 | 2024-10-18 | 100% | 54000 | 52300 | Completed | 1700 | Within Budget | 1
Vendor Portal | Post-Launch Review | David Kim | High | 2025-05-28 | 2025-06-12 |  | 24% | 39000 | 9100 | In Progress | 29900 | Within Budget | 466
HR System Upgrade | Go-Live Preparation | Hannah White | High | 2024-05-10 | 2024-05-24 | 2024-05-23 | 100% | 18000 | 18300 | Completed | -300 | Over Budget | -1
Data Warehouse Build | Budget Review | Stephanie Adams | Medium | 2025-01-10 | 2025-01-18 | 2025-01-19 | 100% | 13000 | 16800 | Completed | -3800 | Over Budget | 1
Onboarding Automation | Backend Development | Robert Garcia | Medium | 2025-05-06 | 2025-07-29 |  | 0% | 168000 | 0 | Not Started | 168000 | Within Budget | 419
Supply Chain Optimization | Technical Architecture | Carlos Mendez | Low | 2024-06-15 | 2024-07-08 | 2024-08-15 | 100% | 50000 | 57500 | Completed | -7500 | Over Budget | 38
Inventory System | Market Research | Sarah Chen | Low | 2024-06-20 | 2024-06-26 | 2024-07-01 | 100% | 9000 | 9700 | Completed | -700 | Over Budget | 5
Cloud Infrastructure | Status Reporting | Rachel Thompson | High | 2025-04-20 | 2025-05-11 |  | 14% | 50000 | 7200 | In Progress | 42800 | Within Budget | 498
Inventory System | Retrospective | Jessica Turner | Medium | 2024-07-03 | 2024-07-10 | 2024-07-04 | 0% | 15000 | 5400 | Cancelled | 9600 | Within Budget | -6
Brand Refresh | Sprint Planning | Rachel Thompson | Critical | 2025-05-13 | 2025-05-19 |  | 91% | 9000 | 9200 | In Progress | -200 | Over Budget | 490
Mobile App Launch | Technical Architecture | Tom Mitchell | High | 2025-04-09 | 2025-04-27 |  | 22% | 46000 | 8600 | In Progress | 37400 | Within Budget | 512
HR System Upgrade | Communication Plan | Olivia Martinez | High | 2024-04-12 | 2024-04-20 |  | 46% | 5000 | 3500 | Delayed | 1500 | Within Budget | 884
Onboarding Automation | Accessibility Audit | Lisa Wang | Low | 2024-11-06 | 2024-11-20 |  | 61% | 15000 | 9200 | Delayed | 5800 | Within Budget | 670
Social Media Revamp | Frontend Development | Elena Rodriguez | Medium | 2024-07-07 | 2024-08-18 | 2024-07-11 | 0% | 64000 | 16100 | Cancelled | 47900 | Within Budget | -38
Product Launch Q2 | API Development | Kevin O'Brien | Medium | 2024-08-23 | 2024-09-07 | 2024-08-31 | 100% | 17000 | 18700 | Completed | -1700 | Over Budget | -7
Training Platform | Stakeholder Interviews | Brian Taylor | Critical | 2024-12-07 | 2024-12-20 | 2024-12-20 | 100% | 44000 | 58400 | Completed | -14400 | Over Budget | 0
Email Platform Migration | Change Management | Daniel Park | Low | 2024-06-17 | 2024-06-28 | 2024-06-21 | 100% | 22000 | 23300 | Completed | -1300 | Over Budget | -7
Vendor Portal | User Training | Lisa Wang | Low | 2025-02-11 | 2025-03-06 |  | 49% | 17000 | 20000 | Delayed | -3000 | Over Budget | 564
Inventory System | User Training | Kevin O'Brien | Critical | 2024-07-31 | 2024-08-30 | 2024-09-29 | 100% | 41000 | 50700 | Completed | -9700 | Over Budget | 30
Training Platform | SEO Optimization | Elena Rodriguez | Critical | 2024-09-08 | 2024-10-01 | 2024-10-25 | 100% | 47000 | 64900 | Completed | -17900 | Over Budget | 24
Email Platform Migration | Requirements Gathering | Kevin O'Brien | High | 2024-06-12 | 2024-06-20 | 2024-06-14 | 10% | 5000 | 900 | Cancelled | 4100 | Within Budget | -6
Training Platform | A/B Testing Setup | Elena Rodriguez | Medium | 2024-04-17 | 2024-05-16 | 2024-05-09 | 100% | 28000 | 32200 | Completed | -4200 | Over Budget | -7
Marketing Automation | Retrospective | Hannah White | High | 2024-12-05 | 2024-12-15 | 2024-12-16 | 100% | 11000 | 9800 | Completed | 1200 | Within Budget | 1
Payment Integration | Security Review | Robert Garcia | Medium | 2024-12-27 | 2025-01-17 | 2025-01-28 | 100% | 49000 | 62700 | Completed | -13700 | Over Budget | 11
API Gateway | Asset Design | Amanda Foster | Low | 2024-08-24 | 2024-09-24 | 2024-09-26 | 100% | 33000 | 29800 | Completed | 3200 | Within Budget | 2
Inventory System | Analytics Integration | Olivia Martinez | High | 2024-10-04 | 2024-11-06 | 2024-10-06 | 25% | 95000 | 36400 | Cancelled | 58600 | Within Budget | -31
Office Relocation | Vendor Evaluation | Ahmed Hassan | Medium | 2024-03-29 | 2024-04-11 | 2024-04-25 | 100% | 23000 | 29300 | Completed | -6300 | Over Budget | 14
Email Platform Migration | Integration Testing | Michael Brown | Low | 2024-02-12 | 2024-03-05 |  | 32% | 49000 | 48500 | Delayed | 500 | Within Budget | 930
Security Audit | Go-Live Preparation | Hannah White | Medium | 2024-09-18 | 2024-10-21 |  | 75% | 91000 | 71300 | Delayed | 19700 | Within Budget | 700
Product Launch Q1 | UI/UX Design | Lisa Wang | Medium | 2024-03-01 | 2024-03-24 |  | 62% | 44000 | 43800 | Delayed | 200 | Within Budget | 911
Security Audit | SEO Optimization | Stephanie Adams | High | 2024-09-25 | 2024-10-20 | 2024-10-21 | 100% | 50000 | 57600 | Completed | -7600 | Over Budget | 1
Cloud Infrastructure | Stakeholder Interviews | Marcus Johnson | High | 2025-04-18 | 2025-05-01 |  | 41% | 12000 | 5700 | In Progress | 6300 | Within Budget | 508
Mobile App Launch | Wireframing | Stephanie Adams | Low | 2024-03-14 | 2024-04-09 | 2024-05-20 | 100% | 18000 | 15800 | Completed | 2200 | Within Budget | 41
Training Platform | Code Review | Natasha Singh | Critical | 2024-12-11 | 2024-12-28 | 2025-01-04 | 100% | 42000 | 35800 | Completed | 6200 | Within Budget | 7
Email Platform Migration | Technical Architecture | Tom Mitchell | High | 2025-05-03 | 2025-05-13 |  | 0% | 9000 | 0 | Not Started | 9000 | Within Budget | 496
Payment Integration | Technical Architecture | Olivia Martinez | Medium | 2024-04-24 | 2024-05-11 | 2024-05-25 | 100% | 10000 | 13600 | Completed | -3600 | Over Budget | 14
Data Warehouse Build | Content Creation | Brian Taylor | Low | 2025-05-24 | 2025-06-25 |  | 76% | 32000 | 28900 | In Progress | 3100 | Within Budget | 453
Brand Refresh | Vendor Evaluation | Amanda Foster | High | 2025-02-18 | 2025-03-16 |  | 22% | 35000 | 42300 | Delayed | -7300 | Over Budget | 554
Social Media Revamp | Iteration Planning | James Wilson | High | 2025-01-10 | 2025-01-21 | 2025-01-17 | 100% | 27000 | 28100 | Completed | -1100 | Over Budget | -4
Onboarding Automation | Documentation | Daniel Park | Medium | 2025-04-24 | 2025-05-14 |  | 0% | 35000 | 0 | Not Started | 35000 | Within Budget | 495
Supply Chain Optimization | Contract Negotiation | Elena Rodriguez | High | 2025-01-02 | 2025-01-27 |  | 27% | 31000 | 19500 | Delayed | 11500 | Within Budget | 602
API Gateway | Deployment Planning | Chris Evans | Medium | 2024-02-26 | 2024-03-17 | 2024-03-21 | 100% | 25000 | 25900 | Completed | -900 | Over Budget | 4
Cloud Infrastructure | Asset Design | Kevin O'Brien | Medium | 2025-05-02 | 2025-05-09 |  | 0% | 9000 | 0 | Not Started | 9000 | Within Budget | 500
Customer Portal | Frontend Development | Tom Mitchell | Medium | 2024-02-18 | 2024-05-10 | 2024-05-11 | 100% | 177000 | 161300 | Completed | 15700 | Within Budget | 1
HR System Upgrade | Stakeholder Interviews | Tom Mitchell | Critical | 2024-01-30 | 2024-02-04 |  | 81% | 12000 | 13100 | Delayed | -1100 | Over Budget | 960
DevOps Pipeline | API Development | Emily Davis | Low | 2024-12-24 | 2025-01-01 | 2025-01-26 | 100% | 8000 | 11100 | Completed | -3100 | Over Budget | 25
ERP Implementation | Infrastructure Setup | Carlos Mendez | Low | 2024-03-07 | 2024-04-11 | 2024-04-16 | 100% | 54000 | 54700 | Completed | -700 | Over Budget | 5
ERP Implementation | Integration Testing | Chris Evans | Low | 2024-07-06 | 2024-08-04 | 2024-08-20 | 100% | 30000 | 41800 | Completed | -11800 | Over Budget | 16
Data Warehouse Build | Post-Launch Review | Hannah White | Medium | 2025-05-09 | 2025-06-09 |  | 43% | 97000 | 49800 | In Progress | 47200 | Within Budget | 469
Customer Portal | Market Research | Amanda Foster | Low | 2025-02-06 | 2025-02-19 | 2025-02-20 | 100% | 15000 | 17100 | Completed | -2100 | Over Budget | 1
Office Relocation | Contract Negotiation | Daniel Park | Medium | 2024-01-13 | 2024-01-28 |  | 82% | 10000 | 5400 | Delayed | 4600 | Within Budget | 967
Website Redesign | Iteration Planning | Ahmed Hassan | Low | 2024-06-12 | 2024-07-16 | 2024-07-29 | 100% | 89000 | 124500 | Completed | -35500 | Over Budget | 13
Email Platform Migration | Requirements Gathering | Sarah Chen | High | 2024-07-24 | 2024-08-06 | 2024-08-21 | 100% | 38000 | 41000 | Completed | -3000 | Over Budget | 15
Cloud Infrastructure | Vendor Evaluation | Olivia Martinez | Low | 2024-04-08 | 2024-04-23 | 2024-04-25 | 100% | 19000 | 20000 | Completed | -1000 | Over Budget | 2
Social Media Revamp | Infrastructure Setup | Amanda Foster | Medium | 2025-05-08 | 2025-05-29 |  | 0% | 38000 | 0 | Not Started | 38000 | Within Budget | 480
Customer Portal | Accessibility Audit | Olivia Martinez | Critical | 2024-01-20 | 2024-02-10 | 2024-02-24 | 100% | 23000 | 22900 | Completed | 100 | Within Budget | 14
DevOps Pipeline | Retrospective | Priya Patel | High | 2024-12-09 | 2024-12-23 | 2025-01-08 | 100% | 42000 | 58000 | Completed | -16000 | Over Budget | 16
Cloud Infrastructure | Risk Assessment | Brian Taylor | High | 2025-02-05 | 2025-03-06 |  | 25% | 24000 | 11600 | On Hold | 12400 | Within Budget | 564
Supply Chain Optimization | Budget Review | Ahmed Hassan | Critical | 2024-07-11 | 2024-07-30 | 2024-08-16 | 100% | 29000 | 35400 | Completed | -6400 | Over Budget | 17
Training Platform | Documentation | Chris Evans | High | 2025-03-25 | 2025-04-08 |  | 88% | 41000 | 34600 | In Progress | 6400 | Within Budget | 531
Customer Portal | Go-Live Preparation | Rachel Thompson | Medium | 2024-07-12 | 2024-07-23 | 2024-08-05 | 100% | 15000 | 16100 | Completed | -1100 | Over Budget | 13
Product Launch Q2 | Monitoring Setup | Jessica Turner | High | 2025-02-04 | 2025-03-04 |  | 68% | 37000 | 12800 | On Hold | 24200 | Within Budget | 566
Payment Integration | Performance Testing | Emily Davis | Medium | 2024-09-17 | 2024-10-07 |  | 30% | 36000 | 23200 | Delayed | 12800 | Within Budget | 714
DevOps Pipeline | Feedback Collection | Natasha Singh | Medium | 2025-06-24 | 2025-07-06 |  | 38% | 29000 | 12800 | In Progress | 16200 | Within Budget | 442
Product Launch Q2 | Frontend Development | Sarah Chen | Low | 2025-04-27 | 2025-07-13 |  | 0% | 159000 | 0 | Not Started | 159000 | Within Budget | 435
Email Platform Migration | Technical Architecture | Michael Brown | Medium | 2024-05-24 | 2024-06-21 | 2024-06-06 | 15% | 48000 | 13300 | Cancelled | 34700 | Within Budget | -15
Annual Report | Wireframing | Michael Brown | Medium | 2025-03-07 | 2025-04-04 |  | 79% | 40000 | 34300 | In Progress | 5700 | Within Budget | 535
Data Warehouse Build | Feedback Collection | Jessica Turner | Medium | 2024-11-26 | 2024-12-27 | 2025-02-08 | 100% | 60000 | 64500 | Completed | -4500 | Over Budget | 43
HR System Upgrade | Analytics Integration | Stephanie Adams | Critical | 2024-11-17 | 2024-12-19 | 2024-11-22 | 25% | 94000 | 10600 | Cancelled | 83400 | Within Budget | -27
DevOps Pipeline | Market Research | Daniel Park | High | 2024-03-30 | 2024-04-05 | 2024-03-29 | 100% | 4000 | 4000 | Completed | 0 | Within Budget | -7
Analytics Dashboard | Contract Negotiation | Hannah White | Medium | 2024-07-22 | 2024-08-15 |  | 83% | 26000 | 31900 | Delayed | -5900 | Over Budget | 767
CRM Migration | Security Review | Tom Mitchell | Medium | 2024-06-17 | 2024-06-29 | 2024-08-05 | 100% | 27000 | 25100 | Completed | 1900 | Within Budget | 37
Chatbot Development | Frontend Development | Lisa Wang | Low | 2024-08-07 | 2024-09-09 |  | 78% | 67000 | 66900 | Delayed | 100 | Within Budget | 742
Payment Integration | Vendor Evaluation | David Kim | High | 2024-11-25 | 2024-12-15 | 2024-12-10 | 100% | 27000 | 25500 | Completed | 1500 | Within Budget | -5
Compliance Overhaul | Database Design | Jennifer Lee | Medium | 2024-08-21 | 2024-09-27 |  | 71% | 84000 | 48500 | Delayed | 35500 | Within Budget | 724
Customer Portal | Status Reporting | Olivia Martinez | Low | 2025-04-01 | 2025-05-04 |  | 0% | 81000 | 0 | Not Started | 81000 | Within Budget | 505
Training Platform | Sprint Planning | Carlos Mendez | High | 2024-11-10 | 2024-11-24 |  | 27% | 18000 | 9300 | Delayed | 8700 | Within Budget | 666
API Gateway | Analytics Integration | Olivia Martinez | Critical | 2025-01-05 | 2025-01-12 |  | 40% | 5000 | 6400 | Delayed | -1400 | Over Budget | 617
Email Platform Migration | Quality Assurance | Hannah White | Medium | 2025-05-18 | 2025-06-21 |  | 0% | 72000 | 0 | Not Started | 72000 | Within Budget | 457
Cloud Infrastructure | Prototype Development | Chris Evans | Medium | 2024-08-07 | 2024-08-29 |  | 30% | 44000 | 47600 | Delayed | -3600 | Over Budget | 753
Supply Chain Optimization | Post-Launch Review | Daniel Park | High | 2024-06-21 | 2024-07-11 | 2024-07-27 | 100% | 45000 | 60600 | Completed | -15600 | Over Budget | 16
Brand Refresh | Deployment Planning | Natasha Singh | Low | 2024-07-08 | 2024-07-19 | 2024-07-09 | 15% | 47000 | 3300 | Cancelled | 43700 | Within Budget | -10
Marketing Automation | Unit Testing | Tom Mitchell | High | 2024-07-30 | 2024-08-24 | 2024-08-18 | 100% | 48000 | 44200 | Completed | 3800 | Within Budget | -6
ERP Implementation | Risk Assessment | Ahmed Hassan | High | 2024-10-29 | 2024-11-17 | 2024-11-17 | 100% | 30000 | 40200 | Completed | -10200 | Over Budget | 0
Analytics Dashboard | Retrospective | Natasha Singh | High | 2024-09-19 | 2024-09-27 | 2024-09-27 | 100% | 3000 | 2700 | Completed | 300 | Within Budget | 0
Compliance Overhaul | Retrospective | Sarah Chen | Critical | 2025-03-20 | 2025-04-03 |  | 0% | 29000 | 0 | Not Started | 29000 | Within Budget | 536
Office Relocation | Risk Assessment | Daniel Park | High | 2024-12-29 | 2025-01-09 | 2024-12-31 | 10% | 33000 | 10400 | Cancelled | 22600 | Within Budget | -9
Product Launch Q1 | Quality Assurance | Daniel Park | Low | 2024-09-28 | 2024-10-29 | 2024-11-11 | 100% | 39000 | 52500 | Completed | -13500 | Over Budget | 13
Chatbot Development | Frontend Development | Rachel Thompson | Medium | 2025-02-16 | 2025-03-31 |  | 34% | 71000 | 23800 | In Progress | 47200 | Within Budget | 539
CRM Migration | Contract Negotiation | Priya Patel | Low | 2024-02-24 | 2024-03-17 | 2024-04-02 | 100% | 27000 | 28000 | Completed | -1000 | Over Budget | 16
Marketing Automation | Feedback Collection | Kevin O'Brien | Medium | 2025-03-09 | 2025-04-06 |  | 82% | 20000 | 15600 | In Progress | 4400 | Within Budget | 533
Supply Chain Optimization | System Configuration | Elena Rodriguez | Critical | 2024-04-13 | 2024-05-13 | 2024-05-14 | 100% | 28000 | 32500 | Completed | -4500 | Over Budget | 1
HR System Upgrade | Infrastructure Setup | David Kim | Critical | 2024-09-26 | 2024-10-27 | 2024-10-25 | 100% | 94000 | 121600 | Completed | -27600 | Over Budget | -2
Product Launch Q2 | Quality Assurance | Stephanie Adams | High | 2024-01-19 | 2024-02-01 | 2024-02-22 | 100% | 34000 | 35400 | Completed | -1400 | Over Budget | 21
Mobile App Launch | Integration Testing | Jennifer Lee | High | 2024-04-02 | 2024-04-17 |  | 39% | 31000 | 39200 | Delayed | -8200 | Over Budget | 887
Cloud Infrastructure | Stakeholder Interviews | Elena Rodriguez | High | 2024-04-12 | 2024-04-23 | 2024-04-15 | 25% | 39000 | 4000 | Cancelled | 35000 | Within Budget | -8
Vendor Portal | Sprint Planning | David Kim | Medium | 2024-03-22 | 2024-03-29 | 2024-03-24 | 10% | 4000 | 1300 | Cancelled | 2700 | Within Budget | -5
Supply Chain Optimization | Backend Development | Amanda Foster | High | 2024-02-13 | 2024-04-27 | 2024-02-26 | 30% | 196000 | 27900 | Cancelled | 168100 | Within Budget | -61
Data Warehouse Build | Vendor Evaluation | Kevin O'Brien | Medium | 2025-04-02 | 2025-04-15 |  | 0% | 47000 | 0 | Not Started | 47000 | Within Budget | 524
HR System Upgrade | Vendor Evaluation | Daniel Park | Medium | 2024-04-07 | 2024-05-09 |  | 51% | 36000 | 30500 | Delayed | 5500 | Within Budget | 865
Mobile App Launch | Prototype Development | Natasha Singh | High | 2025-06-18 | 2025-07-14 |  | 0% | 18000 | 0 | Not Started | 18000 | Within Budget | 434
Onboarding Automation | Deployment Planning | Jessica Turner | Medium | 2024-12-11 | 2025-01-08 | 2025-01-24 | 100% | 27000 | 34200 | Completed | -7200 | Over Budget | 16
Inventory System | Change Management | Natasha Singh | High | 2024-10-28 | 2024-11-23 | 2025-01-06 | 100% | 41000 | 46800 | Completed | -5800 | Over Budget | 44
API Gateway | Status Reporting | Chris Evans | Medium | 2024-01-29 | 2024-02-09 | 2024-03-16 | 100% | 15000 | 19500 | Completed | -4500 | Over Budget | 36
Product Launch Q1 | Sprint Planning | Priya Patel | Medium | 2024-08-08 | 2024-08-20 | 2024-08-21 | 100% | 28000 | 35400 | Completed | -7400 | Over Budget | 1
API Gateway | Requirements Gathering | Michael Brown | Medium | 2025-04-26 | 2025-05-05 |  | 0% | 6000 | 0 | Not Started | 6000 | Within Budget | 504
Marketing Automation | Content Creation | Lisa Wang | Medium | 2025-02-23 | 2025-03-03 |  | 50% | 15000 | 6000 | In Progress | 9000 | Within Budget | 567
Product Launch Q1 | Training Materials | Lisa Wang | High | 2024-12-05 | 2025-01-03 |  | 34% | 39000 | 31900 | Delayed | 7100 | Within Budget | 626
HR System Upgrade | User Training | Chris Evans | Low | 2025-02-24 | 2025-03-06 |  | 62% | 2000 | 800 | On Hold | 1200 | Within Budget | 564
HR System Upgrade | Prototype Development | Ahmed Hassan | Critical | 2024-10-11 | 2024-11-21 | 2024-12-16 | 100% | 86000 | 75200 | Completed | 10800 | Within Budget | 25
Product Launch Q2 | Change Management | James Wilson | Medium | 2024-05-23 | 2024-06-17 | 2024-07-05 | 100% | 26000 | 28600 | Completed | -2600 | Over Budget | 18
Website Redesign | Deployment Planning | Amanda Foster | High | 2024-09-27 | 2024-10-21 |  | 32% | 18000 | 14700 | Delayed | 3300 | Within Budget | 700
Security Audit | API Development | Priya Patel | Low | 2024-02-04 | 2024-02-13 | 2024-02-15 | 100% | 9000 | 8800 | Completed | 200 | Within Budget | 2
Customer Portal | Code Review | Jennifer Lee | Medium | 2024-12-24 | 2025-01-14 | 2025-01-09 | 100% | 14000 | 17300 | Completed | -3300 | Over Budget | -5
Email Platform Migration | Analytics Integration | Natasha Singh | Critical | 2025-01-13 | 2025-02-13 | 2025-02-28 | 100% | 77000 | 66000 | Completed | 11000 | Within Budget | 15
Office Relocation | UI/UX Design | Carlos Mendez | High | 2025-04-09 | 2025-05-22 |  | 0% | 67000 | 0 | Not Started | 67000 | Within Budget | 487
Email Platform Migration | Prototype Development | Priya Patel | Low | 2025-01-28 | 2025-02-20 |  | 60% | 37000 | 6000 | On Hold | 31000 | Within Budget | 578
Inventory System | Communication Plan | Marcus Johnson | Low | 2024-01-21 | 2024-02-24 | 2024-02-03 | 30% | 91000 | 8600 | Cancelled | 82400 | Within Budget | -21
ERP Implementation | Code Review | Stephanie Adams | Low | 2024-07-21 | 2024-08-17 | 2024-08-19 | 100% | 36000 | 48700 | Completed | -12700 | Over Budget | 2
Analytics Dashboard | Analytics Integration | James Wilson | Low | 2024-09-09 | 2024-10-11 | 2024-09-19 | 20% | 55000 | 19000 | Cancelled | 36000 | Within Budget | -22
Performance Review System | Stakeholder Interviews | Daniel Park | Low | 2024-07-18 | 2024-07-30 | 2024-07-25 | 100% | 12000 | 14000 | Completed | -2000 | Over Budget | -5
Product Launch Q2 | Code Review | Robert Garcia | Low | 2025-06-16 | 2025-07-05 |  | 0% | 17000 | 0 | Not Started | 17000 | Within Budget | 443
Chatbot Development | Training Materials | Jennifer Lee | Medium | 2024-12-03 | 2024-12-24 | 2024-12-12 | 0% | 11000 | 2300 | Cancelled | 8700 | Within Budget | -12
API Gateway | Security Review | Lisa Wang | High | 2024-07-21 | 2024-08-23 | 2024-08-24 | 100% | 52000 | 44400 | Completed | 7600 | Within Budget | 1
Inventory System | Accessibility Audit | Robert Garcia | High | 2024-06-03 | 2024-06-20 | 2024-06-16 | 100% | 48000 | 45900 | Completed | 2100 | Within Budget | -4
Mobile App Launch | Security Review | Olivia Martinez | Critical | 2024-02-25 | 2024-03-23 | 2024-03-29 | 100% | 16000 | 18800 | Completed | -2800 | Over Budget | 6
Onboarding Automation | Go-Live Preparation | Jennifer Lee | Medium | 2024-04-22 | 2024-05-01 |  | 71% | 13000 | 11600 | Delayed | 1400 | Within Budget | 873
DevOps Pipeline | Risk Assessment | Kevin O'Brien | Low | 2024-08-17 | 2024-09-03 | 2024-08-20 | 15% | 46000 | 12200 | Cancelled | 33800 | Within Budget | -14
Product Launch Q2 | Backup Configuration | Sarah Chen | Medium | 2024-04-18 | 2024-05-10 |  | 32% | 12000 | 11600 | Delayed | 400 | Within Budget | 864
Social Media Revamp | Competitive Analysis | Marcus Johnson | Low | 2025-06-21 | 2025-07-23 |  | 0% | 93000 | 0 | Not Started | 93000 | Within Budget | 425
Supply Chain Optimization | Post-Launch Review | Hannah White | High | 2025-05-06 | 2025-05-21 |  | 0% | 44000 | 0 | Not Started | 44000 | Within Budget | 488
Budget Planning Tool | Change Management | Lisa Wang | Low | 2024-03-08 | 2024-04-06 |  | 85% | 24000 | 29700 | Delayed | -5700 | Over Budget | 898
Mobile App Launch | Risk Assessment | Elena Rodriguez | Medium | 2024-09-28 | 2024-10-26 | 2024-10-30 | 100% | 23000 | 31400 | Completed | -8400 | Over Budget | 4
Customer Portal | System Configuration | Robert Garcia | Critical | 2024-08-10 | 2024-09-13 | 2024-08-27 | 30% | 82000 | 18300 | Cancelled | 63700 | Within Budget | -17
ERP Implementation | Contract Negotiation | Elena Rodriguez | Low | 2024-02-11 | 2024-03-07 | 2024-04-07 | 100% | 12000 | 10500 | Completed | 1500 | Within Budget | 31
Marketing Automation | Monitoring Setup | Michael Brown | High | 2025-05-31 | 2025-06-14 |  | 0% | 32000 | 0 | Not Started | 32000 | Within Budget | 464
Product Launch Q2 | Bug Fixes | David Kim | Medium | 2024-07-03 | 2024-07-22 | 2024-07-30 | 100% | 15000 | 19200 | Completed | -4200 | Over Budget | 8
Performance Review System | Prototype Development | Rachel Thompson | Medium | 2024-11-03 | 2024-12-07 | 2024-11-06 | 30% | 100000 | 18000 | Cancelled | 82000 | Within Budget | -31
Mobile App Launch | Change Management | Robert Garcia | Medium | 2025-06-04 | 2025-06-15 |  | 0% | 30000 | 0 | Not Started | 30000 | Within Budget | 463
Customer Portal | Change Management | Priya Patel | Low | 2024-10-03 | 2024-10-15 | 2024-10-07 | 30% | 10000 | 900 | Cancelled | 9100 | Within Budget | -8
Analytics Dashboard | Backend Development | Jennifer Lee | Medium | 2025-05-04 | 2025-07-31 |  | 0% | 103000 | 0 | Not Started | 103000 | Within Budget | 417
Supply Chain Optimization | Analytics Integration | Hannah White | Low | 2025-04-14 | 2025-05-08 |  | 0% | 47000 | 0 | Not Started | 47000 | Within Budget | 501
API Gateway | Analytics Integration | Carlos Mendez | Medium | 2024-12-24 | 2025-01-19 |  | 53% | 18000 | 20400 | Delayed | -2400 | Over Budget | 610
Training Platform | Performance Testing | James Wilson | Medium | 2024-06-17 | 2024-07-04 | 2024-06-22 | 20% | 48000 | 16400 | Cancelled | 31600 | Within Budget | -12
Mobile App Launch | Go-Live Preparation | Sarah Chen | Low | 2024-09-01 | 2024-09-09 |  | 60% | 7000 | 6200 | Delayed | 800 | Within Budget | 742
Brand Refresh | Contract Negotiation | Kevin O'Brien | Low | 2024-04-28 | 2024-05-28 | 2024-05-22 | 100% | 38000 | 43400 | Completed | -5400 | Over Budget | -6
Chatbot Development | Status Reporting | Ahmed Hassan | High | 2024-05-06 | 2024-06-07 |  | 58% | 73000 | 57000 | Delayed | 16000 | Within Budget | 836
Security Audit | Requirements Gathering | Sarah Chen | High | 2025-03-19 | 2025-03-27 |  | 22% | 15000 | 3500 | In Progress | 11500 | Within Budget | 543
Email Platform Migration | Frontend Development | Rachel Thompson | Low | 2025-03-09 | 2025-04-15 |  | 0% | 75000 | 0 | Not Started | 75000 | Within Budget | 524
Performance Review System | Post-Launch Review | Emily Davis | Low | 2024-04-04 | 2024-05-09 | 2024-05-11 | 100% | 61000 | 70600 | Completed | -9600 | Over Budget | 2
Email Platform Migration | Frontend Development | Priya Patel | Low | 2025-04-14 | 2025-05-25 |  | 0% | 96000 | 0 | Not Started | 96000 | Within Budget | 484
Annual Report | Feedback Collection | Hannah White | Medium | 2024-01-23 | 2024-02-01 | 2024-02-09 | 100% | 6000 | 7900 | Completed | -1900 | Over Budget | 8
Data Warehouse Build | Integration Testing | Jessica Turner | High | 2025-04-02 | 2025-04-22 |  | 69% | 44000 | 30900 | In Progress | 13100 | Within Budget | 517
Performance Review System | Training Materials | Sarah Chen | Low | 2024-02-19 | 2024-03-08 | 2024-03-08 | 100% | 23000 | 27400 | Completed | -4400 | Over Budget | 0
Inventory System | Database Design | Priya Patel | Low | 2024-03-14 | 2024-04-07 | 2024-05-16 | 100% | 44000 | 61500 | Completed | -17500 | Over Budget | 39
HR System Upgrade | Documentation | Brian Taylor | High | 2025-04-07 | 2025-05-04 |  | 0% | 48000 | 0 | Not Started | 48000 | Within Budget | 505
Website Redesign | Training Materials | Rachel Thompson | Low | 2024-11-29 | 2024-12-06 | 2024-12-08 | 100% | 3000 | 3600 | Completed | -600 | Over Budget | 2
Email Platform Migration | Feedback Collection | Sarah Chen | Medium | 2025-03-13 | 2025-04-13 |  | 0% | 99000 | 0 | Not Started | 99000 | Within Budget | 526
CRM Migration | Prototype Development | Olivia Martinez | High | 2024-12-02 | 2024-12-29 | 2024-12-21 | 100% | 26000 | 29400 | Completed | -3400 | Over Budget | -8
Product Launch Q2 | Analytics Integration | Ahmed Hassan | Critical | 2024-01-18 | 2024-01-27 |  | 81% | 10000 | 6000 | Delayed | 4000 | Within Budget | 968
Social Media Revamp | User Acceptance Testing | Natasha Singh | Low | 2024-03-01 | 2024-03-15 | 2024-03-23 | 100% | 13000 | 15900 | Completed | -2900 | Over Budget | 8
Onboarding Automation | Bug Fixes | Jessica Turner | High | 2024-04-25 | 2024-05-09 | 2024-04-27 | 25% | 35000 | 10100 | Cancelled | 24900 | Within Budget | -12
Customer Portal | Integration Testing | Jessica Turner | Low | 2025-03-13 | 2025-04-12 |  | 0% | 28000 | 0 | Not Started | 28000 | Within Budget | 527
Annual Report | Prototype Development | Carlos Mendez | Medium | 2024-08-31 | 2024-10-09 | 2024-10-12 | 100% | 94000 | 86200 | Completed | 7800 | Within Budget | 3
Budget Planning Tool | User Training | Lisa Wang | Low | 2024-05-28 | 2024-06-13 | 2024-06-17 | 100% | 12000 | 15700 | Completed | -3700 | Over Budget | 4
Analytics Dashboard | Post-Launch Review | Tom Mitchell | High | 2024-08-18 | 2024-08-31 | 2024-09-10 | 100% | 26000 | 35100 | Completed | -9100 | Over Budget | 10
Customer Portal | Documentation | Marcus Johnson | High | 2024-11-15 | 2024-12-09 | 2024-12-09 | 100% | 36000 | 32900 | Completed | 3100 | Within Budget | 0
Mobile App Launch | Technical Architecture | Lisa Wang | Low | 2025-01-22 | 2025-02-21 |  | 85% | 35000 | 33700 | In Progress | 1300 | Within Budget | 577
Product Launch Q1 | Security Review | Sarah Chen | High | 2025-02-16 | 2025-03-09 | 2025-03-10 | 100% | 11000 | 10400 | Completed | 600 | Within Budget | 1
Social Media Revamp | Analytics Integration | Emily Davis | Medium | 2025-05-06 | 2025-06-01 |  | 0% | 44000 | 0 | Not Started | 44000 | Within Budget | 477
Email Platform Migration | Backup Configuration | Natasha Singh | Medium | 2025-04-02 | 2025-04-24 |  | 0% | 10000 | 0 | Not Started | 10000 | Within Budget | 515
Analytics Dashboard | Vendor Evaluation | Stephanie Adams | Critical | 2024-04-12 | 2024-05-09 | 2024-05-09 | 100% | 38000 | 42800 | Completed | -4800 | Over Budget | 0
Marketing Automation | Asset Design | Natasha Singh | Medium | 2024-09-27 | 2024-10-05 |  | 43% | 13000 | 15000 | Delayed | -2000 | Over Budget | 716
HR System Upgrade | Wireframing | David Kim | Medium | 2024-03-22 | 2024-04-20 | 2024-04-23 | 100% | 48000 | 41600 | Completed | 6400 | Within Budget | 3
Inventory System | Unit Testing | Marcus Johnson | High | 2024-05-23 | 2024-06-23 | 2024-08-06 | 100% | 51000 | 67000 | Completed | -16000 | Over Budget | 44
DevOps Pipeline | Retrospective | Ahmed Hassan | Critical | 2024-01-22 | 2024-02-03 | 2024-02-28 | 100% | 12000 | 11600 | Completed | 400 | Within Budget | 25
Mobile App Launch | Bug Fixes | Carlos Mendez | Medium | 2024-04-21 | 2024-05-22 | 2024-05-22 | 100% | 51000 | 61800 | Completed | -10800 | Over Budget | 0
Website Redesign | Bug Fixes | Stephanie Adams | Critical | 2025-06-17 | 2025-07-11 |  | 0% | 16000 | 0 | Not Started | 16000 | Within Budget | 437
Data Warehouse Build | Retrospective | Elena Rodriguez | High | 2025-03-08 | 2025-03-18 |  | 67% | 11000 | 12900 | Delayed | -1900 | Over Budget | 552
Email Platform Migration | Data Migration | Olivia Martinez | Medium | 2024-04-15 | 2024-06-21 |  | 42% | 169000 | 196900 | Delayed | -27900 | Over Budget | 822
Payment Integration | Data Migration | Marcus Johnson | High | 2025-03-03 | 2025-04-08 |  | 68% | 73000 | 81300 | Delayed | -8300 | Over Budget | 531
Inventory System | Data Migration | Daniel Park | Low | 2024-07-08 | 2024-10-06 | 2024-10-09 | 100% | 80000 | 87800 | Completed | -7800 | Over Budget | 3
Product Launch Q1 | Wireframing | Emily Davis | Low | 2024-11-21 | 2024-12-05 | 2024-11-23 | 30% | 18000 | 2700 | Cancelled | 15300 | Within Budget | -12
Product Launch Q1 | Content Creation | Michael Brown | Medium | 2024-02-29 | 2024-03-30 | 2024-04-30 | 100% | 39000 | 33400 | Completed | 5600 | Within Budget | 31
Vendor Portal | Documentation | Lisa Wang | Low | 2024-03-14 | 2024-04-08 | 2024-04-22 | 100% | 50000 | 44400 | Completed | 5600 | Within Budget | 14
Brand Refresh | UI/UX Design | Hannah White | Low | 2024-09-09 | 2024-10-08 | 2024-10-03 | 100% | 46000 | 40600 | Completed | 5400 | Within Budget | -5
Product Launch Q2 | Unit Testing | Natasha Singh | Low | 2024-10-11 | 2024-11-03 | 2024-11-26 | 100% | 24000 | 27500 | Completed | -3500 | Over Budget | 23
Supply Chain Optimization | Quality Assurance | Ahmed Hassan | High | 2024-01-06 | 2024-02-10 | 2024-03-26 | 100% | 76000 | 65500 | Completed | 10500 | Within Budget | 45
Budget Planning Tool | Post-Launch Review | Brian Taylor | Medium | 2024-08-01 | 2024-08-23 | 2024-08-23 | 100% | 25000 | 24500 | Completed | 500 | Within Budget | 0
ERP Implementation | Database Design | Jennifer Lee | Medium | 2024-06-21 | 2024-08-04 | 2024-09-17 | 100% | 40000 | 50200 | Completed | -10200 | Over Budget | 44
Compliance Overhaul | Integration Testing | Ahmed Hassan | Low | 2025-01-25 | 2025-02-06 |  | 77% | 50000 | 39200 | Delayed | 10800 | Within Budget | 592
Brand Refresh | Retrospective | Stephanie Adams | Medium | 2024-12-27 | 2025-01-06 |  | 43% | 6000 | 6300 | Delayed | -300 | Over Budget | 623
Annual Report | Integration Testing | Chris Evans | Medium | 2024-08-03 | 2024-08-16 | 2024-08-09 | 0% | 21000 | 2700 | Cancelled | 18300 | Within Budget | -7
ERP Implementation | Status Reporting | Elena Rodriguez | Low | 2024-07-05 | 2024-07-30 | 2024-08-02 | 100% | 48000 | 57800 | Completed | -9800 | Over Budget | 3
Social Media Revamp | Deployment Planning | Rachel Thompson | Medium | 2024-12-31 | 2025-01-28 |  | 20% | 23000 | 21800 | Delayed | 1200 | Within Budget | 601
Mobile App Launch | Content Creation | Tom Mitchell | Medium | 2024-06-22 | 2024-07-27 |  | 85% | 100000 | 91500 | Delayed | 8500 | Within Budget | 786
Budget Planning Tool | Content Creation | Marcus Johnson | Medium | 2024-05-15 | 2024-05-30 | 2024-05-31 | 100% | 40000 | 51500 | Completed | -11500 | Over Budget | 1
Product Launch Q1 | Deployment Planning | Jessica Turner | Medium | 2024-09-08 | 2024-09-18 | 2024-10-26 | 100% | 4000 | 4300 | Completed | -300 | Over Budget | 38
DevOps Pipeline | Quality Assurance | Michael Brown | Low | 2025-05-05 | 2025-05-17 |  | 0% | 42000 | 0 | Not Started | 42000 | Within Budget | 492
Security Audit | Documentation | Michael Brown | Low | 2025-01-16 | 2025-02-05 | 2025-02-09 | 100% | 20000 | 18500 | Completed | 1500 | Within Budget | 4
CRM Migration | User Training | Olivia Martinez | High | 2024-09-06 | 2024-10-11 | 2024-10-12 | 100% | 42000 | 55600 | Completed | -13600 | Over Budget | 1
Brand Refresh | Status Reporting | Emily Davis | Low | 2025-05-05 | 2025-06-02 |  | 0% | 48000 | 0 | Not Started | 48000 | Within Budget | 476
Mobile App Launch | Performance Testing | Robert Garcia | Medium | 2025-06-06 | 2025-06-28 |  | 0% | 39000 | 0 | Not Started | 39000 | Within Budget | 450
Email Platform Migration | Security Review | Chris Evans | Medium | 2024-11-22 | 2024-12-20 | 2024-12-22 | 100% | 41000 | 37200 | Completed | 3800 | Within Budget | 2
Payment Integration | Monitoring Setup | Tom Mitchell | High | 2025-06-13 | 2025-07-07 |  | 0% | 48000 | 0 | Not Started | 48000 | Within Budget | 441
Vendor Portal | User Acceptance Testing | Lisa Wang | Medium | 2025-05-09 | 2025-05-28 |  | 0% | 36000 | 0 | Not Started | 36000 | Within Budget | 481
Cloud Infrastructure | UI/UX Design | David Kim | High | 2024-05-23 | 2024-07-05 | 2024-07-19 | 100% | 44000 | 43600 | Completed | 400 | Within Budget | 14
Data Warehouse Build | Optimization | James Wilson | Medium | 2024-11-14 | 2024-11-22 | 2024-12-10 | 100% | 4000 | 4100 | Completed | -100 | Over Budget | 18
Annual Report | Asset Design | Brian Taylor | Medium | 2025-06-12 | 2025-06-29 |  | 0% | 10000 | 0 | Not Started | 10000 | Within Budget | 449
Inventory System | UI/UX Design | Olivia Martinez | Medium | 2024-09-18 | 2024-10-27 | 2024-11-14 | 100% | 85000 | 89400 | Completed | -4400 | Over Budget | 18
Vendor Portal | Frontend Development | Carlos Mendez | Low | 2024-01-05 | 2024-02-17 | 2024-01-24 | 30% | 72000 | 24400 | Cancelled | 47600 | Within Budget | -24
Inventory System | Asset Design | Elena Rodriguez | High | 2024-08-27 | 2024-09-11 | 2024-09-16 | 100% | 39000 | 39500 | Completed | -500 | Over Budget | 5
Payment Integration | Accessibility Audit | Robert Garcia | Medium | 2025-02-27 | 2025-03-22 |  | 40% | 18000 | 3600 | On Hold | 14400 | Within Budget | 548
Inventory System | Analytics Integration | Tom Mitchell | Low | 2024-10-12 | 2024-11-07 | 2024-11-25 | 100% | 34000 | 41100 | Completed | -7100 | Over Budget | 18
Marketing Automation | User Training | Amanda Foster | Low | 2024-12-17 | 2024-12-27 | 2024-12-27 | 100% | 2000 | 2000 | Completed | 0 | Within Budget | 0
Payment Integration | Sprint Planning | Natasha Singh | Medium | 2024-01-20 | 2024-01-26 | 2024-01-21 | 30% | 12000 | 4600 | Cancelled | 7400 | Within Budget | -5
Email Platform Migration | Content Creation | Elena Rodriguez | Medium | 2024-08-15 | 2024-09-04 | 2024-09-27 | 100% | 25000 | 34000 | Completed | -9000 | Over Budget | 23
Supply Chain Optimization | Post-Launch Review | Jennifer Lee | Medium | 2025-05-09 | 2025-05-18 |  | 0% | 14000 | 0 | Not Started | 14000 | Within Budget | 491
Customer Portal | Unit Testing | Jennifer Lee | Medium | 2025-03-13 | 2025-04-08 |  | 71% | 16000 | 9700 | In Progress | 6300 | Within Budget | 531
Performance Review System | Infrastructure Setup | Marcus Johnson | Medium | 2024-10-06 | 2024-11-10 | 2024-12-15 | 100% | 97000 | 94600 | Completed | 2400 | Within Budget | 35
Analytics Dashboard | Backup Configuration | David Kim | Medium | 2024-11-04 | 2024-11-20 |  | 27% | 44000 | 34500 | Delayed | 9500 | Within Budget | 670
Customer Portal | Backend Development | Daniel Park | High | 2024-03-09 | 2024-04-25 | 2024-04-20 | 100% | 32000 | 35600 | Completed | -3600 | Over Budget | -5
HR System Upgrade | Code Review | Lisa Wang | Medium | 2025-04-06 | 2025-04-16 |  | 0% | 15000 | 0 | Not Started | 15000 | Within Budget | 523
Training Platform | Contract Negotiation | Emily Davis | Low | 2024-12-30 | 2025-01-21 |  | 64% | 13000 | 6100 | On Hold | 6900 | Within Budget | 608
ERP Implementation | User Acceptance Testing | Jessica Turner | Low | 2024-06-12 | 2024-06-24 |  | 79% | 23000 | 18500 | Delayed | 4500 | Within Budget | 819
Email Platform Migration | User Training | Carlos Mendez | Medium | 2025-03-25 | 2025-04-11 |  | 33% | 28000 | 7500 | In Progress | 20500 | Within Budget | 528
API Gateway | Feedback Collection | Hannah White | Medium | 2024-05-06 | 2024-06-03 | 2024-06-05 | 100% | 23000 | 26600 | Completed | -3600 | Over Budget | 2
Security Audit | Integration Testing | Jessica Turner | Low | 2025-04-12 | 2025-05-01 |  | 0% | 37000 | 0 | Not Started | 37000 | Within Budget | 508
Annual Report | Unit Testing | Natasha Singh | Medium | 2024-04-05 | 2024-04-17 | 2024-04-10 | 15% | 30000 | 5400 | Cancelled | 24600 | Within Budget | -7
Brand Refresh | Retrospective | Olivia Martinez | High | 2024-12-04 | 2024-12-10 |  | 37% | 15000 | 13700 | Delayed | 1300 | Within Budget | 650
HR System Upgrade | Compliance Check | Ahmed Hassan | Medium | 2024-02-06 | 2024-02-24 | 2024-03-21 | 100% | 34000 | 46100 | Completed | -12100 | Over Budget | 26
Product Launch Q1 | Prototype Development | Hannah White | Medium | 2024-11-14 | 2024-12-09 | 2024-12-10 | 100% | 12000 | 11700 | Completed | 300 | Within Budget | 1
Training Platform | Database Design | Jennifer Lee | Low | 2024-02-28 | 2024-03-30 | 2024-03-04 | 30% | 61000 | 9500 | Cancelled | 51500 | Within Budget | -26
Data Warehouse Build | Go-Live Preparation | Kevin O'Brien | Critical | 2024-04-09 | 2024-04-23 | 2024-04-24 | 100% | 25000 | 24500 | Completed | 500 | Within Budget | 1
Email Platform Migration | Analytics Integration | Marcus Johnson | Low | 2024-01-19 | 2024-02-06 |  | 40% | 39000 | 45000 | Delayed | -6000 | Over Budget | 958
DevOps Pipeline | Frontend Development | Stephanie Adams | Medium | 2024-07-06 | 2024-08-20 | 2024-08-14 | 100% | 63000 | 76100 | Completed | -13100 | Over Budget | -6
Onboarding Automation | A/B Testing Setup | Jessica Turner | Medium | 2024-07-13 | 2024-07-29 | 2024-07-27 | 100% | 48000 | 42700 | Completed | 5300 | Within Budget | -2
Analytics Dashboard | UI/UX Design | Sarah Chen | Low | 2024-01-06 | 2024-02-14 |  | 29% | 60000 | 57800 | Delayed | 2200 | Within Budget | 950
Email Platform Migration | Post-Launch Review | Hannah White | Medium | 2024-05-24 | 2024-06-01 | 2024-05-29 | 100% | 2000 | 2000 | Completed | 0 | Within Budget | -3
Budget Planning Tool | Bug Fixes | Sarah Chen | High | 2024-01-03 | 2024-01-29 | 2024-02-01 | 100% | 39000 | 35600 | Completed | 3400 | Within Budget | 3
Payment Integration | Code Review | Hannah White | Low | 2024-01-02 | 2024-01-15 |  | 78% | 18000 | 20600 | Delayed | -2600 | Over Budget | 980
Data Warehouse Build | Training Materials | Carlos Mendez | Low | 2024-01-24 | 2024-02-02 | 2024-02-29 | 100% | 5000 | 4400 | Completed | 600 | Within Budget | 27
Onboarding Automation | User Acceptance Testing | Carlos Mendez | Low | 2024-02-11 | 2024-02-18 | 2024-02-13 | 20% | 10000 | 1300 | Cancelled | 8700 | Within Budget | -5
Analytics Dashboard | Database Design | Priya Patel | High | 2024-04-07 | 2024-05-05 | 2024-04-29 | 100% | 10000 | 9400 | Completed | 600 | Within Budget | -6
DevOps Pipeline | Integration Testing | Stephanie Adams | Low | 2024-08-26 | 2024-09-03 | 2024-08-29 | 20% | 11000 | 1000 | Cancelled | 10000 | Within Budget | -5
Training Platform | Wireframing | Michael Brown | Medium | 2025-01-01 | 2025-02-11 |  | 69% | 95000 | 72800 | Delayed | 22200 | Within Budget | 587
Budget Planning Tool | Content Creation | Tom Mitchell | Medium | 2025-05-27 | 2025-06-13 |  | 0% | 27000 | 0 | Not Started | 27000 | Within Budget | 465
CRM Migration | Data Migration | Natasha Singh | High | 2024-10-08 | 2024-11-22 | 2024-11-14 | 100% | 94000 | 114600 | Completed | -20600 | Over Budget | -8
Product Launch Q2 | Asset Design | Priya Patel | Low | 2025-04-22 | 2025-05-27 |  | 28% | 54000 | 15700 | In Progress | 38300 | Within Budget | 482
Inventory System | Training Materials | James Wilson | High | 2024-11-29 | 2024-12-14 |  | 50% | 26000 | 14900 | Delayed | 11100 | Within Budget | 646
Chatbot Development | Compliance Check | Hannah White | Medium | 2024-12-05 | 2024-12-27 |  | 39% | 23000 | 16000 | Delayed | 7000 | Within Budget | 633
Product Launch Q2 | Monitoring Setup | Michael Brown | Medium | 2024-08-19 | 2024-09-19 | 2024-09-27 | 100% | 100000 | 129100 | Completed | -29100 | Over Budget | 8
Performance Review System | Performance Testing | Priya Patel | Low | 2025-04-29 | 2025-05-17 |  | 0% | 11000 | 0 | Not Started | 11000 | Within Budget | 492
Product Launch Q1 | Frontend Development | Lisa Wang | Low | 2025-06-18 | 2025-07-18 |  | 0% | 24000 | 0 | Not Started | 24000 | Within Budget | 430
Budget Planning Tool | Iteration Planning | Ahmed Hassan | Medium | 2025-03-02 | 2025-03-18 |  | 77% | 24000 | 24400 | Delayed | -400 | Over Budget | 552
Budget Planning Tool | API Development | Daniel Park | Low | 2025-05-13 | 2025-06-17 |  | 51% | 51000 | 27700 | In Progress | 23300 | Within Budget | 461
Supply Chain Optimization | Wireframing | Jessica Turner | Medium | 2024-06-27 | 2024-08-03 | 2024-09-03 | 100% | 36000 | 36900 | Completed | -900 | Over Budget | 31
Analytics Dashboard | Optimization | Brian Taylor | Low | 2024-03-29 | 2024-04-18 | 2024-05-16 | 100% | 20000 | 20500 | Completed | -500 | Over Budget | 28
Product Launch Q1 | Monitoring Setup | Brian Taylor | Low | 2025-04-27 | 2025-05-22 |  | 0% | 29000 | 0 | Not Started | 29000 | Within Budget | 487
Website Redesign | Optimization | Elena Rodriguez | Medium | 2024-07-25 | 2024-08-25 | 2024-08-28 | 100% | 53000 | 46400 | Completed | 6600 | Within Budget | 3
HR System Upgrade | Communication Plan | Emily Davis | Low | 2025-03-22 | 2025-04-23 |  | 59% | 61000 | 35900 | In Progress | 25100 | Within Budget | 516
HR System Upgrade | Vendor Evaluation | Emily Davis | Low | 2025-03-21 | 2025-04-25 |  | 11% | 32000 | 2900 | In Progress | 29100 | Within Budget | 514
Budget Planning Tool | Requirements Gathering | Marcus Johnson | High | 2025-01-01 | 2025-01-15 |  | 63% | 23000 | 13200 | Delayed | 9800 | Within Budget | 614
Website Redesign | Backend Development | Elena Rodriguez | Critical | 2024-01-21 | 2024-03-12 | 2024-03-17 | 100% | 53000 | 72400 | Completed | -19400 | Over Budget | 5
Training Platform | Status Reporting | Jennifer Lee | High | 2024-04-20 | 2024-05-02 |  | 33% | 16000 | 20100 | Delayed | -4100 | Over Budget | 872
Annual Report | Market Research | Emily Davis | High | 2025-04-24 | 2025-05-04 |  | 0% | 3000 | 0 | Not Started | 3000 | Within Budget | 505
DevOps Pipeline | Stakeholder Interviews | Robert Garcia | Low | 2025-02-16 | 2025-02-25 |  | 71% | 3000 | 1900 | Delayed | 1100 | Within Budget | 573
CRM Migration | Security Review | Daniel Park | Low | 2025-04-10 | 2025-05-10 |  | 0% | 10000 | 0 | Not Started | 10000 | Within Budget | 499
Product Launch Q1 | Vendor Evaluation | Amanda Foster | High | 2025-05-25 | 2025-06-25 |  | 0% | 82000 | 0 | Not Started | 82000 | Within Budget | 453
Supply Chain Optimization | UI/UX Design | Jennifer Lee | Low | 2024-11-09 | 2024-12-08 | 2024-12-10 | 100% | 31000 | 29600 | Completed | 1400 | Within Budget | 2
Social Media Revamp | Content Creation | Sarah Chen | High | 2025-01-29 | 2025-03-05 | 2025-04-19 | 100% | 48000 | 50200 | Completed | -2200 | Over Budget | 45
Chatbot Development | User Acceptance Testing | Michael Brown | Medium | 2024-09-16 | 2024-10-10 | 2024-09-28 | 15% | 17000 | 4800 | Cancelled | 12200 | Within Budget | -12
Performance Review System | Iteration Planning | Daniel Park | Low | 2024-11-25 | 2024-12-23 |  | 30% | 30000 | 27900 | Delayed | 2100 | Within Budget | 637
Training Platform | Security Review | David Kim | Medium | 2024-11-18 | 2024-12-09 | 2024-11-21 | 30% | 49000 | 18000 | Cancelled | 31000 | Within Budget | -18
Budget Planning Tool | Competitive Analysis | Hannah White | High | 2025-04-29 | 2025-05-28 |  | 0% | 21000 | 0 | Not Started | 21000 | Within Budget | 481
Marketing Automation | Accessibility Audit | Priya Patel | High | 2025-03-11 | 2025-04-01 |  | 39% | 10000 | 4500 | In Progress | 5500 | Within Budget | 538
Onboarding Automation | Prototype Development | Amanda Foster | High | 2024-11-21 | 2024-12-16 | 2024-12-22 | 100% | 21000 | 28100 | Completed | -7100 | Over Budget | 6
Vendor Portal | Analytics Integration | Daniel Park | High | 2024-11-02 | 2024-11-26 | 2024-11-26 | 100% | 43000 | 44900 | Completed | -1900 | Over Budget | 0
DevOps Pipeline | Technical Architecture | Kevin O'Brien | Critical | 2025-03-17 | 2025-04-13 |  | 0% | 37000 | 0 | Not Started | 37000 | Within Budget | 526
Inventory System | Sprint Planning | Jennifer Lee | Medium | 2024-09-20 | 2024-10-05 |  | 75% | 39000 | 41200 | Delayed | -2200 | Over Budget | 716
Marketing Automation | Wireframing | Natasha Singh | Medium | 2025-05-16 | 2025-06-19 |  | 0% | 96000 | 0 | Not Started | 96000 | Within Budget | 459
Marketing Automation | Change Management | Ahmed Hassan | Critical | 2024-08-15 | 2024-08-23 | 2024-08-31 | 100% | 11000 | 12500 | Completed | -1500 | Over Budget | 8
Customer Portal | User Acceptance Testing | Natasha Singh | Low | 2024-09-29 | 2024-10-22 | 2024-11-09 | 100% | 10000 | 12200 | Completed | -2200 | Over Budget | 18
Formulas:
Timeline = IF([Actual End Date]="",TODAY()-[Planned End Date],[Actual End Date]-[Planned End Date])